## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Construction of different components of Baragharia PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000026/2023-2024 | 93/JD | 25/04/2023 | 22/10/2023 | SCEC BOENTER KDAS JOINT VENTURE | 431.11 | 111.72 | 25.92 | 55
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 1839/JD | 15/12/2023 |  | Resource Division | 12.71 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003248664, Reference ID : 403090252] |  |  | BILL/01650/2023-2024 | BP/23-24/170 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003249150, Reference ID : 403091826] |  |  | BILL/01651/2023-2024 | BP/23-24/170 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.88 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS,at TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000417/2023-2024 | 1331/NMD | 08/08/2023 | 07/09/2023 | B.B. CONCERNED | 24.52 | 7.98 | 32.54 | 90
Total | [13 empty] | 502.11 | 119.7 | 23.84