## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of fuel (Diesel) for vehicle no. WB-71B-9430 for the month of February-2024 |  |  | BILL/00097/2024-2025 | BP-2024-25-64 | 14/05/2024 |  | FILL & SMILE | 0.23 | 0 | 0 | null
2 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00130/2024-2025 | BP-2024-25-97 | 22/05/2024 |  | FILL & SMILE | 0.36 | 0 | 0 | null
3 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00131/2024-2025 | BP-2024-25-98 | 22/05/2024 |  | FILL & SMILE | 0.28 | 0 | 0 | null
4 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of March,2024 Vide Vehicle no-WB71B9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00320/2024-2025 | BP-2024-25-182 | 28/06/2024 |  | FILL & SMILE | 0.14 | 0 | 0 | null
5 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of April,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00321/2024-2025 | BP-2024-25-183 | 28/06/2024 |  | FILL & SMILE | 0.29 | 0 | 0 | null
6 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Engine oil, Gear Oil and Kool plus Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte |  |  | BILL/00324/2024-2025 | BP-2024-25-181 | 28/06/2024 |  | FILL & SMILE | 0.07 | 0 | 0 | null
7 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00384/2024-2025 | BP-2024-25-269 | 30/07/2024 |  | FILL & SMILE | 0.19 | 0 | 0 | null
8 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month January'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00402/2024-2025 | BP-2024-25-240 | 26/07/2024 |  | FILL & SMILE | 0.19 | 0 | 0 | null
9 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00523/2024-2025 | BP-2024-25-294 | 14/08/2024 |  | FILL & SMILE | 0.21 | 0 | 0 | null
10 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 |  | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-I) PWSS i.e. OHR,TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. of North Bengal Circle-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2024-2025 | 936/JD | 07/08/2024 | 03/06/2025 | SUJIT KUMAR SAHA | 183.05 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.07.2024 to 31.08.2024)" | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000091/2024-2025 | 531/JD | 28/06/2024 | 27/08/2024 | GURUKUL INFOTECH | 3.16 | 1.58 | 50 | 0
14 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission. Period from 01/08/2024 to 31/01/2025. | Assistant Engineer | Junior Engineer | ORD/000093/2024-2025 | 125/JSSD | 18/07/2024 | 14/01/2025 | APIKUL ALI | 0.88 | 0.55 | 62.25 | 0
15 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 25/01/2025 | APIKUL ALI | 0.88 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-II) PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 800/JD. | 24/07/2023 | 20/01/2024 | GHANASHYAM SARKAR | 281.55 | 93.88 | 33.34 | 40
17 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 27/07/2024 | APIKUL ALI | 0.88 | 0.45 | 50.77 | 70
18 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 27/07/2024 | DHIRAJ BISWAS | 0.88 | 0.77 | 87.15 | 0
19 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1090/JD | 24/08/2023 |  | Resource Division | 24.92 | 0 | 0 | 0
20 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 2070/JD | 10/01/2024 |  | Resource Division | 17.24 | 0 | 0 | 0
21 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Infrastructure development cost for new service connection at ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109306 Reference ID : 860301266 |  |  | BILL/00409/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.48 | 0 | 0 | null
22 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | New Service Connection Charge for ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424001 Reference ID : 403230049 |  |  | BILL/00410/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | null
23 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | New Service Connection Charge for ODLABARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266395, Reference ID : 403105528] |  |  | BILL/01281/2023-2024 | 23-24/160&168 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.91 | 0 | 0 | 0
24 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Infrastructure Cost for ODLABARI TEA GARDEN,T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093886, Reference ID : 860285546] |  |  | BILL/01282/2023-2024 | 23-24/160&168 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0 | 0
25 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ODLABARI TEA GARDEN PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000757/2023-2024 | 1585/NMD | 08/09/2023 | 08/10/2023 | CHOWDHURY AND BASU ENTERPRISE | 42.08 | 5.65 | 13.42 | 35
Total | [13 empty] | 612.59 | 102.87 | 16.79