## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 |  | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.43 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain , Land Development etc. at HW Site for Kumarpara PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000074/2024-2025 | 1296/JD | 05/09/2024 | 04/11/2024 | M/S BOSE ENTERPRISE | 22.73 | 0 | 0 | 0
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 2nd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer |  | ORD/000084/2024-2025 | 803/RWS | 20/08/2024 | 19/09/2024 | RANA DEY | 7.43 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 3rd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer |  | ORD/000102/2024-2025 | 839/RWS | 29/08/2024 | 28/09/2024 | SUKUMAR KUNDU | 7.46 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Construction of different components of Kumarpara PWSS i.e, TW, Pump Houses, Water distribution network , OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2023-2024 | 945/JD | 08/08/2023 | 04/02/2024 | SCEC BOENTER KDAS JOINT VENTURE | 601.28 | 144.11 | 23.97 | 25
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 57/JD | 09/04/2024 |  | Resource Division | 31.48 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 2052/JD | 09/01/2024 |  | Resource Division | 14.78 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376070 Reference ID : 403191653 |  |  | BILL/00152/2024-2025 | BP/24-25/78 | 06/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.13 | 0 | 0 | null
10 | JALPAIGURI | Maynaguri | Northern Mechanical | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376595 Reference ID : 403191665 |  |  | BILL/00154/2024-2025 | BP/24-25/78 | 06/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.49 | 0 | 0 | null
11 | JALPAIGURI | Maynaguri | Northern Mechanical | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003435868 Reference ID : 403237472 |  |  | BILL/00460/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0 | null
12 | JALPAIGURI | Maynaguri | Northern Mechanical | Kumarpara Piped Water Supply Scheme. | SM/18491 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUMARPARA PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000609/2023-2024 | 1342/NMD | 08/08/2023 | 07/09/2023 | DAS ENTERPRISE | 32.55 | 10.12 | 31.1 | 50
Total | [13 empty] | 791.44 | 154.23 | 19.49