## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of August 2024. |  |  | BILL/00760/2024-2025 | BP-2024-25-448 | 03/10/2024 | 03/10/2024 | FILL & SMILE | 0.09 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of September 2024. |  |  | BILL/00852/2024-2025 | BP-2024-25-484 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of October 2024. |  |  | BILL/00985/2024-2025 | BP-2024-25-549 | 17/12/2024 | 17/12/2024 | FILL & SMILE | 0.16 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19/08/2024 to 18/02/2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000079/2024-2025 | 1025/JD | 16/08/2024 | 16/02/2025 | AJIJUL HAQUE | 0.88 | 0.91 | 103.2 | 0
5 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Construction of different components of Salugara PWSS zone-II i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000282/2023-2024 | 1256/JD | 13/09/2023 | 11/03/2024 | S. N. POLYMERS PVT. LTD. | 335.88 | 61.22 | 18.23 | 25
6 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Construction of different components of Salugara PWSS zone-I i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2023-2024 | 1258/JD | 13/09/2023 | 11/03/2024 | S. N. POLYMERS PVT. LTD. | 346.56 | 100.54 | 29.01 | 35
7 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19.02.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000689/2024-2025 | 53/HQ/JD | 18/02/2025 | 31/03/2025 | AJIJUL HAQUE | 0.2 | 0.05 | 26.53 | 0
8 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1102/JD | 24/08/2023 | 24/08/2023 | Resource Division | 65.27 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1507/JD | 13/10/2023 | 13/10/2023 | Resource Division | 32.56 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. II, under POWER HOUSE CCC , [APPLICATION NO. 4003334685, Reference ID : 403158908] |  |  | BILL/02038/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.9 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-II,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334683, Reference ID : 403158637] |  |  | BILL/02039/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.7 | 0 | 0 | 0
12 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334689, Reference ID : 403158907] |  |  | BILL/02040/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.17 | 0 | 0 | 0
13 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Infrastructure Cost for SALUGARA , T/W-II, ZONE-II under POWER HOUSE CCC [APPLICATION NO. 4003341484 , Reference ID : 403163817] |  |  | BILL/02041/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
14 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
15 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
16 | JALPAIGURI | Rajganj | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME | SM/18625 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SALUGARA PWSS, ZONE-I AND II, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000660/2023-2024 | 1474/NMD | 17/08/2023 | 01/01/2026 | CHOWDHURY AND BASU ENTERPRISE | 43.27 | 29.47 | 68.12 | 85
Total | [13 empty] | 1442.41 | 192.2 | 13.32