## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 |  | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Construction of different components of Damdim Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1257/JD | 13/09/2023 | 11/03/2024 | PRASENJIT BASAK | 297.11 | 94.3 | 31.74 | 40
4 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Estimate for Balance work of Water Distribution Network in Damdim Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2023-2024 | 569/JSSD | 05/03/2024 | 04/04/2024 | PRABIR SHOME | 9.05 | 3.9 | 43.04 | 100
5 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 2017/JD | 09/01/2024 |  | Resource Division | 12.02 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No.I, under ODLABARI CCC, [APPLICATION NO. 4003325562, Reference ID : 403151430] |  |  | BILL/01983/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000098645, Reference ID : 860290455] |  |  | BILL/01984/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003325572, Reference ID : 403151429] |  |  | BILL/01985/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000098644, Reference ID : 860290454] |  |  | BILL/01986/2023-2024 | BP/23-24/306 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAMDIM TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000465/2023-2024 | 1441/NMD | 10/08/2023 | 09/09/2023 | DILIP MAHATO | 25.34 | 0 | 0 | 75
Total | [13 empty] | 415.13 | 98.2 | 23.65