## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Distribution System and Functional Household Tap Connection (FHTC) for Paharpur Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000026/2024-2025 | 739/JD | 26/07/2024 | 09/10/2024 | GOUTAM DAS | 108.29 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Construction of different components of Paharpur Zone - I Piped Water Supply Scheme i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 1820/JD | 14/12/2023 | 11/06/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 616.92 | 70.95 | 11.5 | 50
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1081/JD | 24/08/2023 |  | Resource Division | 40.23 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 2005/JD | 08/01/2024 |  | Resource Division | 20.68 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341737, Reference ID : 403171420] |  |  | BILL/02152/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.18 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033441732, Reference ID : 403172479] |  |  | BILL/02153/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.37 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-I, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001416/2023-2024 | 487/NMD | 12/02/2024 | 13/03/2024 | SUMON ELECTRICAL | 23.55 | 9.58 | 40.69 | 60
Total | [13 empty] | 823.22 | 80.54 | 9.78