## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Construction of Intake Well for Sub-Surface Water Source at River Bed of Diana under Nagrakata Block of Jalpaiguri District i.c.w Chengmari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000740/2023-2024 | 2495/JD | 28/02/2024 | 20/03/2024 | GOUTAM DAS | 37.37 | 18.74 | 50.15 | 100
2 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHENGMARI TG AREA PWSS, TW no 1 to 9 in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000869/2023-2024 | 1817/NMD | 01/11/2023 | 01/12/2023 | CONCORD ENGINEERING | 103.77 | 0 | 0 | 0
Total | [13 empty] | 141.14 | 18.74 | 13.28