## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | Providing F.H.T.C. connection in the command area at SINGIMARI PASCHIMPAR W/S Scheme (Part-G) under Cooch Behar Sadar Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000309/2021-2022 | 938/CD | 31/12/2021 | 14/02/2022 | MATARA CONSTRUCTION CO. | 1.75 | 1.75 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | Operation & Maintenence of pipeline & other misc works related to pipeline for Singimari Paschimpar W/S Scheme Under Cooch Behar Sadar Sub Division, P.H.E. Dte.(Period From 01/02/2022 to 31/01/2023) . | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000392/2021-2022 | 1151/CD | 31/01/2022 | 26/01/2023 | BIJOY ROY | 4.31 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | FHTC |  |  | VCH/000101/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.28 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | Providing house connection of drinking water to the household of command area under Singimari Paschimpar W/S Scheme(Part-D) of Cooch Behar Division, PHE Dte. under Jaldhara Programme |  |  | VCH/000116/2021-2022 | null | 20/04/2021 |  | MATARA CONSTRUCTION CO. | 4.62 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | Providing house connection of drinking water to the household of command area under Singimari Paschimpar W/S Scheme(Part-B) of Cooch Behar Division, PHE Dte. under Jaldhara Programme |  |  | VCH/000117/2021-2022 | null | 20/04/2021 |  | MATARA CONSTRUCTION CO. | 4.59 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | Providing house connection of drinking water to the house hold of Command area under Singimari Paschimpar PWSS under Cooch Behar Division, PHED PART-E |  |  | VCH/000128/2021-2022 | null | 21/04/2021 |  | SWAPAN SAHA | 9.48 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | FHTC, LAYING P/ LINE AT NATABARI PWSS |  |  | VCH/000185/2022-2023 | BP_87_22_23 | 21/06/2022 |  | SHREE RANI SATI ENTERPRISE | 9.53 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | HIRING VECHILE |  |  | VCH/000402/2022-2023 | BP-22-23-137 | 14/07/2022 |  | TANMAY CHOUDHURY | 0.21 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | FHTC AT SINGIMARI PASCHIMPAR |  |  | VCH/000526/2021-2022 | BP-2021-22-112 | 28/07/2021 |  | SWAPAN SAHA | 9.48 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | fhtc singimari paschimpar |  |  | VCH/000550/2021-2022 | BP-2021-22-83 | 27/07/2021 |  | MATARA CONSTRUCTION CO. | 4.62 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | FHTC SINGIMARI PASCHIM PAR |  |  | VCH/000593/2021-2022 | BP-2021-22-79 | 27/07/2021 |  | MATARA CONSTRUCTION CO. | 4.59 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | PROVIDING HOUSE CONNECTION OF DRINKI9NG WATER TO THE HOUSEHOLD OF COMMAND AREA UNDER SINGIMARI PASCHIMPAR W.S.S. ( PART - A) OF COB DIVN PHED UNDER JALDHARA PROG. |  |  | VCH/000666/2020-2021 | null | 14/01/2021 |  | SWAPAN SAHA | 4.75 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | laying of pipeline & other allied work related to FHTC under JJM Programme for Putimari Phuleswari PWSS under Cooch Behar Division, P.H.E. Dte. |  |  | VCH/000884/2021-2022 | BP-2021-22-296 | 14/11/2021 |  | GHOSH AND SAHA CONSTRUCTION | 45.71 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | fhtc |  |  | VCH/001375/2021-2022 | BP-2021-22-395 | 22/02/2022 |  | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 19.68 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | fhtc |  |  | VCH/001376/2021-2022 | BP-2021-22-396 | 22/02/2022 |  | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 5.03 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | SM/07157 | Retrofitting | fhtc |  |  | VCH/001377/2021-2022 | BP-2021-22-406 | 24/02/2022 |  | SANJAY MANDAL | 5.01 | 0 | 0 | 0
Total | [13 empty] | 189.32 | 1.75 | 0.93