## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing 140 nos. F.H.T.C. Connection in the command area at Kalapani P.W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000315/2021-2022 | 454/SD | 29/12/2021 | 13/01/2022 | SWAPAN KUMAR ROY | 4.93 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 1190/CD | 01/02/2022 |  | Resource Division | 0.77 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | UPLOADING CHARGES , RELATED TO FHTC JAL JEEVAN MISSION IN PRESENCE OF JJM LOGING AUTHORITY UNDER COOCH BEHAR DivISION PHED |  |  | VCH/000154/2021-2022 | 280 | 16/11/2021 |  | PRIYANKA MANDAL | 0.97 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Prov. fhtc at kalpani |  |  | VCH/000239/2021-2022 | 11 | 12/05/2021 |  | SIDHARTHA ROY | 4.66 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing house Connection for Salmara PWSS under Cooch Behar Division, P.H.E. Dte. |  |  | VCH/000697/2021-2022 | null | 13/09/2021 |  | TAPAN CHANDA | 32.47 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing house connection of drinking water to the household of command area under Kalapani PWSS under Cooch Behar Division, PHED (Part-B) |  |  | VCH/000715/2020-2021 | null | 28/01/2021 |  | SIDHARTHA ROY | 11.84 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing house connection of drinking water to the household of command area under Kalapani W/S Scheme(Part-A) under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme. |  |  | VCH/000718/2020-2021 | null | 28/01/2021 |  | SIDHARTHA ROY | 4.79 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing house connection for Mashaldanga PWSS under Cooch Behar Division, P.H.E. Dte. |  |  | VCH/000803/2021-2022 | null | 08/10/2021 |  | MS BIDYUT SARKAR | 20.29 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing functional household tap connection 120 nos in KHARIKABARI PWSS under Mathabhanga Sub Division, PHE Dte. under jaldhara Programme. |  |  | VCH/000863/2021-2022 | 289 | 20/11/2021 |  | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 5.14 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | Providing house connection of drinking water to the house hold of command area under Kalpani PWSS under Cooch Behar Division, PHED Dte under Jaldhara Programme |  |  | VCH/000924/2020-2021 | null | 18/03/2021 |  | SIDHARTHA ROY | 4.66 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | FHTC AT KALAPANI |  |  | VCH/000929/2021-2022 | BP-2021-22-195 | 11/10/2021 |  | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 5.03 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | FHTC KALAPANI |  |  | VCH/000931/2021-2022 | BP-2021-22-197 | 11/10/2021 |  | BIJOY ROY | 5.06 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | FHTC AT |  |  | VCH/000986/2021-2022 | BP-2021-22-265 | 30/10/2021 |  | GEETA CONSTRUCTION | 21.37 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | fhtc |  |  | VCH/001006/2021-2022 | BP-2021-22-269 | 30/10/2021 |  | NABIN DEBNATH | 21.26 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | FHTC |  |  | VCH/001025/2021-2022 | BP-2021_22_199 | 11/10/2021 |  | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 0.02 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | fhtc kalapani |  |  | VCH/001122/2021-2022 | BP-2021-22-322 | 09/12/2021 |  | SWAPAN KUMAR ROY | 18.21 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | fhtc |  |  | VCH/001123/2021-2022 | BP-2021-22-322 | 09/12/2021 |  | SWAPAN KUMAR ROY | 5.72 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | water testing report |  |  | VCH/001139/2021-2022 | BP-2021-22-330 | 13/12/2021 |  | GREEN ECONOMY INISTIVES PVT LTD | 0.03 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | SM/07160 | Retrofitting | cost of meterial |  |  | VCH/001170/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.72 | 0 | 0 | 0
Total | [13 empty] | 172.95 | 0 | 0