## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | Providing 150nos. F.H.T.C. Connection in the command area at Ekmukha W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000100/2022-2023 | 75/SD | 13/05/2022 | 12/06/2022 | BISWAJIT GUHA | 4.77 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | Operation & Maintenence of pipeline & other misc works related to pipeline for Ekmukha W/S Scheme Under Cooch Behar Sadar Sub Division, P.H.E. Dte.(Period From 01/02/2022 to 31/01/2023) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000393/2021-2022 | 1152/CD | 31/01/2022 | 26/01/2023 | BISWAJIT GUHA | 4.46 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | Providing house connection of drinking water to the household of command area under Ekmukha PWSS under Cooch Behar Division, PHED Part-D |  |  | VCH/000143/2021-2022 | null | 03/05/2021 |  | BISWAJIT GUHA | 9.39 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | Providing house connection of drinking water to the household of command area under Ekmukha PWSS under Cooch Behar Division, PHED Part-D |  |  | VCH/000145/2021-2022 | null | 04/05/2021 |  | BISWAJIT GUHA | 9.39 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | add |  |  | VCH/000561/2021-2022 | BP-2021-22-120 | 04/08/2021 |  | GENESIS | 7.68 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC SANTOSH PUR |  |  | VCH/000588/2021-2022 | BP-2021-22-93 | 28/07/2021 |  | NANDA DULAL GHOSH | 9.39 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC SANTOSH PUR |  |  | VCH/000589/2021-2022 | BP-2021-22-93 | 28/07/2021 |  | NANDA DULAL GHOSH | 0.42 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC SINGIMARI BHETAGURI |  |  | VCH/000599/2021-2022 | BP-2021-22-128 | 12/08/2021 |  | MALAY KR.DEB | 5.99 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC SINGIMARI PASCHIMPAT |  |  | VCH/000686/2021-2022 | BP-2021_22_128 | 12/08/2021 |  | MALAY KR.DEB | 0.09 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | fhtc ekmuka |  |  | VCH/000689/2022-2023 | 79 | 01/08/2022 |  | BISWAJIT GUHA | 3.4 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | SHIFTING PIPE LINE DAMAGED DUE TO WIDENING OF ROAD WITH PROVIDING FHTC AT NAKKATIGACHHI PWS |  |  | VCH/000712/2021-2022 | null | 14/09/2021 |  | ASHIM KUMAR CHAKRABORTY | 29.59 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | PROVIDING FHTC UNDER CHILAKHANA PWS P-C |  |  | VCH/000713/2021-2022 | null | 14/09/2021 |  | KHOKAN DAS | 8.13 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | LAYING PIPE.LINE & OTHER ALLIED WRKS RELATED TO FHTC UNDER JJM PROGRAMME FOR EKMUKHA PWSS |  |  | VCH/000771/2021-2022 | null | 01/10/2021 |  | MS SSB CONSTRUCTION CO | 61.79 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | Providing house connection of drinking water to the household of command area under Ekmukha PWSS under Cooch Behar Division, PHED Part-D |  |  | VCH/000932/2020-2021 | null | 18/03/2021 |  | BISWAJIT GUHA | 9.39 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | fhtc |  |  | VCH/000937/2021-2022 | BP-2021-22-203 | 11/10/2021 |  | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 9.75 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC |  |  | VCH/000975/2021-2022 | BP-2021-22-254 | 30/10/2021 |  | SWAPAN KR.SARKAR | 10.1 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC AT EKMUKHA |  |  | VCH/000984/2021-2022 | BP-2021-22-263 | 30/10/2021 |  | SHYAMAL NATH | 12.12 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | fhtc |  |  | VCH/001007/2021-2022 | BP-2021-22-269 | 30/10/2021 |  | NABIN DEBNATH | 13.01 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | fhtc |  |  | VCH/001141/2021-2022 | BP-2021-22-332 | 21/12/2021 |  | GOUTAM KUMAR DAS | 4.08 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | cost of meterial |  |  | VCH/001151/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.59 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | cost metaral |  |  | VCH/001187/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.03 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC AT EKMUKHA |  |  | VCH/001331/2020-2021 | BP-2021-22-222 | 11/10/2021 |  | NABIN DEBNATH | 5.05 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | SM/08143 | Retrofitting | FHTC AT |  |  | VCH/001334/2020-2021 | BP-2021-22-225 | 11/10/2021 |  | MS SURAJIT MAJUMDER | 12.31 | 0 | 0 | 0
Total | [13 empty] | 235.93 | 0 | 0