## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | EXC. OF DIFFT. WORK AT NAHARHAT BANDAR PWSS |  |  | BILL/00552/2023-2024 | BP-232-P2 | 26/06/2023 |  | GHOSH AND SAHA CONSTRUCTION | 0.8 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | FHTC AT DAUAGURI PWSS |  |  | BILL/00575/2023-2024 | BP-211-P | 06/06/2023 |  | PARITOSH PANDIT | 1.98 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | Providing FHTC & Laying P/Line at PAKHIHAGA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000020/2022-2023 | 36/CD | 07/04/2022 | 22/05/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 41.87 | 35.73 | 85.34 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in PAKHIHAGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000286/2021-2022 | 330/MTB | 04/01/2022 | 19/01/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 4.99 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | fhtc |  |  | VCH/001383/2021-2022 | BP-2021-22-398 | 22/02/2022 |  | GHOSH AND SAHA CONSTRUCTION | 40.61 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | fhtc |  |  | VCH/001588/2021-2022 | BP-2021_22_407 | 02/03/2022 |  | RAJIB CHAKRABORTY | 5.01 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | FHTC |  |  | VCH/001663/2021-2022 | BP_2021_22_483 | 30/03/2022 |  | GOUTAM KUMAR DAS | 6.96 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | SM/08150 | Retrofitting | FHTC |  |  | VCH/001767/2021-2022 | BP-2021_22_454 | 16/03/2022 |  | TAPAN CHANDA | 2.29 | 0 | 0 | 0
Total | [13 empty] | 104.51 | 35.73 | 34.19