## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Providing House connection for PETLA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000043/2021-2022 | 242/CD | 06/08/2021 | 05/09/2021 | HIRAK CONSTRUCTION | 10.1 | 10.1 | 100 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Execution of different works related to PETLA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000075/2023-2024 | 410/CD | 23/05/2023 | 22/06/2023 | RAHAMAN ENTERPRISE | 62.36 | 10.85 | 17.4 | 65
3 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Providing FHTC Site Pump House Boundary Wall SSPost with soak pit & New UPVC/DI/GI Pipe line and other allied works (PART ¿B) at PETLA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000273/2021-2022 | 952/CD | 31/12/2021 | 31/03/2022 | HIRAK CONSTRUCTION | 127.19 | 65.09 | 51.18 | 50
4 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Construction of 250 cum OHR Providing FHTC & New UPVC/DI Pipe line & other allied works (PART ¿A) at PETLA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000276/2021-2022 | 955/CD | 31/12/2021 | 27/10/2022 | S & P ENTERPRISE | 108.26 | 48.39 | 44.7 | 79
5 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Cooch Behar-I & II, Dinhata-I & II & Sitai Block) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000320/2021-2022 | 1653/CD | 31/03/2022 | 15/05/2022 | DEBNATH ENTERPRISE | 1.64 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Petla H/W Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000516/2021-2022 | 1564/CD | 23/03/2022 | 07/04/2022 | DAFFODIL | 2.95 | 5.9 | 200 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 730/CD | 01/12/2021 |  | Resource Division | 11 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2021-2022 | 1189/CD | 01/02/2022 |  | Resource Division | 1.1 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 168/CD | 27/04/2023 |  | Resource Division | 28.04 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | fhtc |  |  | VCH/000070/2022-2023 | BP-22_23-56 | 28/04/2022 |  | SHREE RANI SATI ENTERPRISE | 40.55 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | SOIL INVESTIGAITON IN PETLA |  |  | VCH/000197/2022-2023 | BP_103_22_23 | 21/06/2022 |  | G MITRA & ASSOCIATES | 1.17 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | CONST OF 350 OHR AT PETLA |  |  | VCH/000995/2022-2023 | 350 | 22/10/2022 |  | S AND P ENTERPRISE | 27.93 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GOSANIMARI TW NO VIII PETLA TW NO III |  |  | BILL/00009/2023-2024 | BP-2023-24-12 | 27/04/2023 |  | WBSEDCL | 1.47 | 0 | 0 | 0
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | "Supply, delivery & installation of Electro Mechanical Components at PETLA W/S Scheme, T.W No. II(Replacement), under NMD-II, PHE, Dte. in the dist. of Coochbehar" | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000459/2020-2021 | 717/CMSD | 16/10/2020 | 15/11/2020 | MUSTAFI CONCERN | 2.61 | 2.61 | 100 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Petla Water Supply Scheme. | SM/09295 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGUMENTATION of Petla PWSS, TW no .I(REPLACEMENT) in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000749/2022-2023 | 140/NMD-II | 17/01/2023 | 16/02/2023 | M/S ROYAL ENTERPRISE | 6.34 | 6.3 | 99.36 | 100
Total | [13 empty] | 432.71 | 149.25 | 34.49