## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | HIRING OF DISEL VEHICLE FOR COOCH BRHAR DIVISION, PHED |  |  | BILL/00584/2022-2023 | BP-543-2022-23 | 29/12/2022 |  | AJAD HOSSAIN | 0.36 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | hiring maxicab for survey in cob district |  |  | BILL/00596/2022-2023 | BP-648-2022-23 | 23/01/2023 |  | SUKANTA BISWAS | 0.75 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | HIRING VEHICLE OF COB DIVN, PHED |  |  | BILL/00600/2022-2023 | BP-630-2022-23 | 17/01/2023 |  | PARAUDDIN MIAH | 0.57 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | HIRING DISEL VEHICLE OF BOLERO MAXI CAB FOR O/O THE A.Engg./RWS, PHED |  |  | BILL/00641/2022-2023 | BP-781-2022-23 | 14/03/2023 |  | AJAD HOSSAIN | 0.17 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | FHTC AND OTHER ALLIED WORKS AT PWSS |  |  | BILL/00671/2022-2023 | BP-679-22-23-P1 | 13/02/2023 |  | DAS ENTERPRISE | 0.06 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of TAKAGACH PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000082/2022-2023 | 290/CD | 31/05/2022 | 20/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.89 | 4.89 | 100 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works related to TAKAGACH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000234/2022-2023 | 720/CD | 27/08/2022 | 11/10/2022 | MS SSB CONSTRUCTION CO | 25.39 | 13 | 51.22 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soakpit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿B) at TAKAGACH PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000243/2021-2022 | 892/CD | 24/12/2021 | 23/04/2022 | MS DGB ENTERPRISE | 136.16 | 108.61 | 79.76 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Construction of 450 cum OHR Providing FHTC & New UPVC Pipe line & other allied works at TAKAGACH PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000244/2021-2022 | 893/CD | 24/12/2021 | 20/10/2022 | MS SSB CONSTRUCTION CO | 268.42 | 117.51 | 43.78 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Providing FHTC & other allied works at TAKAGACH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000412/2022-2023 | 1223/CD | 28/11/2022 | 27/01/2023 | MS SSB CONSTRUCTION CO | 47.35 | 23.37 | 49.34 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Temporary Water Supply & Sanitary arrangement for Karnival of Durga Puja (Date-07/10/2022) under Cooch Behar Division, PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000423/2022-2023 | 1057/CD | 04/10/2022 | 07/10/2022 | BIJOY ROY | 0.95 | 0 | 0 | 100
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Takagachh 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000514/2021-2022 | 1562/CD | 23/03/2022 | 07/04/2022 | SWAPAN KUMAR ROY | 2.95 | 2.95 | 100 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Providing FHTC & other allied works at TAKAGACH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000514/2022-2023 | 1651/CD | 10/02/2023 | 12/03/2023 | M/S A. B. ENTERPRISE | 18.64 | 18.63 | 99.97 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Execution of different works related to TAKAGACH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000787/2022-2023 | 1863/CD | 14/03/2023 | 13/04/2023 | KARTICK CH SEAL | 46.81 | 31 | 66.22 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 489/CD | 07/07/2022 |  | Resource Division | 18.48 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 787/CD | 07/12/2021 |  | Resource Division | 16.35 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 116/CD | 26/04/2023 |  | Resource Division | 23.61 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 135/CD | 27/04/2023 |  | Resource Division | 22.63 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 1181/CD | 01/02/2022 |  | Resource Division | 0.83 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | fhtc |  |  | VCH/000110/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.23 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | SOIL INVEIGATION TAKAGACHH |  |  | VCH/000388/2022-2023 | BP-22-23-122 | 11/07/2022 |  | G MITRA & ASSOCIATES | 1.23 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works related PWSS under JAL JEEVAN MISSION |  |  | VCH/000670/2022-2023 | 341 | 25/10/2022 |  | NARAYAN CHANDRA BANIK | 12.28 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | fhtc kharimala khagrabari |  |  | VCH/001587/2021-2022 | BP-2021_22_408 | 02/03/2022 |  | ASHIM KUMAR CHAKRABORTY | 49.77 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | COST OF PIPE |  |  | VCH/001638/2021-2022 | BP_2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 137.99 | 0 | 0 | 0
25 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | NEW SERVICE CONNECTION FOR TAKAGAHH (AUG) PWSS, PH-III |  |  | BILL/00198/2024-2025 | BP-53/24-25 | 29/04/2024 |  | WBSEDCL | 6.89 | 0 | 0 | null
26 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Takagach Water Supply Scheme TW No.I Replacement under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000751/2022-2023 | 146/NMD-II | 17/01/2023 | 06/02/2023 | M/S ANJALI ENTERPRISE | 4.17 | 4.05 | 97.07 | 0
27 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Takagach piped water supply scheme. | SM/09301 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Takagach water supply scheme, TW no III of under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000836/2023-2024 | 2417/NMD-II | 10/08/2023 | 09/09/2023 | M/S D G B ENTERPRISE | 11.32 | 0 | 0 | 80
Total | [13 empty] | 859.26 | 324 | 37.71