## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | EXC. OF DIFF WORK AT CHHAT RAMPUR PWSS |  |  | BILL/00527/2023-2024 | BP-25-P2 | 17/04/2023 |  | GOUTAM KUMAR DAS | 4.98 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Execution of different works related to KAWARDARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000029/2023-2024 | 381/CD | 23/05/2023 | 22/07/2023 | SEKHAR GHOSAL | 25.71 | 14.43 | 56.13 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Providing FHTC & Laying of Pipe line & Sinking of Big Dia Tubewell at 3rd Site of KAUWARDARA PWSS under JAL JEEVAN MISSION (PART ¿C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000188/2022-2023 | 662/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 24.37 | 24.3 | 99.73 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Providing FHTC, Construction of boundary wall, repairing of reservior,baoundary wall and laying new UPVC pipe line and other allied works at in-connection with augmentation KAUWARDARA PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000428/2021-2022 | 1524/CD | 15/03/2022 | 13/06/2022 | SHIBA ENTERPRISE | 125.23 | 102.96 | 82.22 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Providing FHTC, Construction of boundary wall, repairing of reservior,baoundary wall and laying new UPVC pipe line and other allied works at in-connection with augmentation KAUWARDARA PWSS under Cooch Behar Division, PHED. .(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000432/2021-2022 | 1527/CD | 15/03/2022 | 13/06/2022 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 123.94 | 88.34 | 71.27 | 84
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 1106/CD | 27/01/2022 |  | Resource Division | 60.69 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 1377/CD | 22/12/2022 |  | Resource Division | 72.32 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 1471/CD | 16/01/2023 |  | Resource Division | 22.9 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT KAWARDERA W/SS TW III |  |  | BILL/00017/2023-2024 | BP-2023-24-94 | 15/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KAUWADARA TW no III in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000760/2022-2023 | 178/NMD-II | 19/01/2023 | 18/02/2023 | TAPAN BISWAS | 10.74 | 10.07 | 93.75 | 80
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Continuation Carrying out preventive as well as breakdown maintenance of chlorine machines ( Hydaulic Diaphragm based or other ) for asserting disinfection of different rural piped water supply schemes at Mathabhanga II Block in the dist of Cooch Behar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000930/2020-2021 | 514/CMSD | 28/08/2020 | 03/09/2020 | ALPHA ENTERPRISE | 0.77 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Continuation for Carrying out preventive as well as breakdown maintenance of chlorine machines ( Hydaulic Diaphragm based or other ) for asserting disinfection of different rural piped water supply schemes at Mathabhanga II Block in the dist of Cooch Behar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000931/2020-2021 | 1215/CMSD | 26/02/2021 | 26/07/2021 | ALPHA ENTERPRISE | 0.65 | 0 | 0 | 0
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Kauardara Water Supply Scheme | SM/09808 | Augmentation | Continuation Carrying out preventive as well as breakdown maintenance of chlorine machines ( Hydaulic Diaphragm based or other ) for asserting disinfection of different rural piped water supply schemes at Mathabhanga II Block in the dist of Cooch Behar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001042/2019-2020 | 1927/CMSD | 27/02/2020 | 25/08/2020 | ALPHA ENTERPRISE | 0.77 | 0 | 0 | 0
Total | [13 empty] | 529.83 | 240.1 | 45.32