## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | QUOTATION FOR SERVICE CONNTION BHOGMARA PWSS |  |  | BILL/00425/2023-2024 | null | 21/08/2023 |  | WBSEDCL | 2.21 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | quatation for new service connection bhogmara pwss tw no 1 |  |  | BILL/00714/2023-2024 | BP-562 | 11/10/2023 |  | WBSEDCL | 2.15 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | quotation for new service connction at bhogmara pwss twno ii |  |  | BILL/00715/2023-2024 | BP-563 | 11/10/2023 |  | WBSEDCL | 2.84 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Construction of Boundary wall, Pump house at Head Work site and laying of Pipe line and other allied works at BHOGMARA PWSS Under Cooch Behar division P.H.E.Dte.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000003/2022-2023 | 19/CD | 07/04/2022 | 05/08/2022 | SWAPAN KUMAR ROY | 80.93 | 70.9 | 87.61 | 49
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Construction of OHR(250 Cum.) including rising main and laying of Distribution system at BHOGMARA PWSS Under Cooch Behar division P.H.E.Dte.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000040/2022-2023 | 98/CD | 18/04/2022 | 12/02/2023 | MS DGB ENTERPRISE | 134.91 | 115.37 | 85.51 | 65
6 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Execution of different works related to BHOGMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000125/2023-2024 | 668/CD | 14/07/2023 | 11/12/2023 | SWAPAN KUMAR ROY | 98.59 | 80.38 | 81.53 | 64
7 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Providing FHTC & Construction of pump house, Boundarry wall (2nd t/w site) and laying of Pipe line other allied works at BHOGMARA PWSS under JAL JEEVAN MISSION. (Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000197/2022-2023 | 672/CD | 23/08/2022 | 22/10/2022 | SWAPAN KUMAR ROY | 91.64 | 68.36 | 74.6 | 8
8 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of BHOGMARA T/W I & II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000453/2021-2022 | 1440/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 21.4 | 19.52 | 91.2 | 1
10 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Execution of different works related to BHOGMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000489/2023-2024 | 291/CD | 09/02/2024 | 09/04/2024 | SWAPAN KUMAR ROY | 44.97 | 0 | 0 | 40
11 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Soil investigation work for the proposed "Overhead reservoir" at Bhogmara PWSS under Mathabhanga Sub-Division, P.H.E. Dte | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000583/2021-2022 | 466/MTB | 04/03/2022 | 19/03/2022 | G. TECH INDIA | 0.57 | 0.51 | 89.05 | 0
12 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 185/CD | 27/04/2023 |  | Resource Division | 10.62 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bhogmara Water Supply Scheme TW No.- I and,II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001047/2023-2024 | 2698/NMD-II | 15/09/2023 | 15/10/2023 | DEY ENTERPRISE (MALDA) | 21.27 | 0 | 0 | 100
Total | [13 empty] | 20301.39 | 355.03 | 1.75