## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Laying of DI pipe to new alignment and others allied works due to widening of PWD roads from Sitai more to Sitalkuchi of Bara Kaimari PWSS under Cooch Behar Diviion, PHE Dte. |  |  | ORD/000006/2017-2018 | 2422/CD | 23/02/2018 | 24/04/2018 | JHANTU MANDAL | 26.57 | 5.38 | 20.25 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC, Repairing of Boundary wall, Pump house & Blower room, and laying of Pipe line and other allied works in-connection with augmentation of BARA KAIMARI PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000035/2022-2023 | 92/CD | 18/04/2022 | 16/08/2022 | BRISTI CONSTRUCTION | 117.32 | 75.6 | 64.44 | 81
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC Construction P. House Sinking Big Dia Tubewll New Laying of Pipe Line and other allied works at AUG. PAYAMARI PWSS under Cooch Behar Division, PHED PART - B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000038/2022-2023 | 96/CD | 18/04/2022 | 16/08/2022 | M/S S.DAS AND ENTERPRISE | 118.61 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing house hold tap connection of drinking water to the household of command area under BARO KAIMARI WATER SUPPLY SCHEME under Mathabhanga Sub-Division, P.H.E.Dte. Under JALSWAPNA PRAKALPA. |  |  | ORD/000065/2021-2022 | 112/MTB | 09/08/2021 | 24/08/2021 | SUBODH ROY & SONS | 5.05 | 5.05 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC, laying of Pipe line and other allied works at BARO KAIMARI PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000073/2022-2023 | 270/CD | 24/05/2022 | 08/07/2022 | SUBODH ROY & SONS | 16.54 | 16.19 | 97.92 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection within command area of Mahishmuri Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme.Part-E | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000101/2022-2023 | 47/MTB | 02/05/2022 | 17/05/2022 | NABIN DEBNATH | 4.96 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection within command area under BARA KAIMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000117/2022-2023 | 131/MTB | 23/06/2022 | 08/07/2022 | SUBODH ROY & SONS | 4.77 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC & other allied works at BARO KAIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000152/2022-2023 | 563/CD | 29/07/2022 | 27/09/2022 | SANJAY MANDAL | 20.71 | 20.71 | 99.99 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC & other allied works at BARO KAIMARI PWSS under JAL JEEVAN MISSION PART Z | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000153/2022-2023 | 564/CD | 29/07/2022 | 27/09/2022 | NABIN DEBNATH | 20.74 | 20.74 | 100 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection (unmetered) 120 nos. in BARA KAIMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. |  |  | ORD/000176/2021-2022 | 178/MTB | 06/09/2021 | 21/09/2021 | SUBODH ROY & SONS | 5.06 | 5.03 | 99.23 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Sinking of Big Dia Tubewell at Baro Kaimari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000181/2022-2023 | 655/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 6.2 | 53.08 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Laying of pipe line and other allied work related to pipe line at Bara Kaimari PWSS under Mathabhanga Sub-Division, PHE Dte. JJM Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000448/2022-2023 | 221/MTB | 26/07/2022 | 25/08/2022 | SUBODH ROY & SONS | 4.87 | 4.87 | 100 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 67/CD | 12/04/2022 |  | Resource Division | 8.79 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 363/CD | 15/06/2022 |  | Resource Division | 1.4 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1375/CD | 22/12/2022 |  | Resource Division | 97.09 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC BARA KAIMARI |  |  | VCH/000395/2022-2023 | BP-22-23-128 | 11/07/2022 |  | M/S. NITYAGOPAL BANIK | 102.54 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC BARA KAIMARI |  |  | VCH/000419/2022-2023 | BP-22-23-153 | 26/07/2022 |  | NABIN DEBNATH | 103.88 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | SUPPLY OF UPVC SINGIMARI BHETAGURI |  |  | VCH/000425/2022-2023 | BP-22-23-161 | 30/07/2022 |  | SWAPAN KUMAR ROY | 2.95 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC AT SOULMARI PWSS |  |  | VCH/000566/2022-2023 | 166 | 10/08/2022 |  | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 20.73 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | BARA SOULMARI |  |  | VCH/001068/2022-2023 | 167 | 10/08/2022 |  | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 0.13 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | COST OF PIPE |  |  | VCH/001694/2021-2022 | BP_2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 34.78 | 0 | 0 | 0
22 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BARA KAIMARI (AUG) TW NO- III |  |  | BILL/00024/2023-2024 | BP-2023-24-13 | 27/04/2023 |  | WBSEDCL | 1.34 | 0 | 0 | 0
23 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augumentation of BARA KAIMARI water supply scheme, TW no I of Zone-I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001033/2023-2024 | 2665/NMD-II | 04/09/2023 | 04/10/2023 | M/S ANJALI ENTERPRISE | 10.71 | 9 | 84.04 | 100
Total | [13 empty] | 741.22 | 168.77 | 22.77