## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | EXC. OF DIFFT. WORK T CHANDAMARI PWSS |  |  | BILL/00525/2023-2024 | BP-28-P | 17/04/2023 |  | GEETA CONSTRUCTION | 6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | UPLOAD CHARGES (MOBILE APPS) |  |  | BILL/00548/2023-2024 | BP-16,29,31-37 | 17/04/2023 |  | BIPASHA MAHANTA BANIK | 8.86 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Execution of different works related to SINGIMARI BHETAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000037/2023-2024 | 374/CD | 23/05/2023 | 22/07/2023 | MALAY KR.DEB | 43.42 | 36.13 | 83.23 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Execution of different works related to S. BHETAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000130/2023-2024 | 671/CD | 14/07/2023 | 12/09/2023 | MALAY KR.DEB | 47.2 | 37.19 | 78.8 | 95
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Sinking of Big Dia Tubewell at Singimari Bhetaguri PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000180/2022-2023 | 654/CD | 23/08/2022 | 22/10/2022 | MS SSB CONSTRUCTION CO | 11.69 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Sinking of Big Dia Tubewell at 2ND Site of SINGIMARI BHETAGURI ZONE ¿ I PWSS under JAL JEEVAN MISSION (RT) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000242/2022-2023 | 730/CD | 27/08/2022 | 11/10/2022 | MS DD ENTERPRISE | 11.68 | 11.66 | 99.8 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | PROVIDING F.H.T.C FOR SINGIMARI BHETAGURI PIPED WATER SUPPLY SCHEME AND SUPPLY OF CIDF SPECIALS IN COOCH BEHAR DIVISION P.H.E DTE | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000278/2022-2023 | 908/CD | 26/09/2022 | 26/10/2022 | M/S A. B. ENTERPRISE | 9.76 | 9.76 | 100 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SINGIMARI BHETAGURI PWSS under JAL JEEVAN MISSION Z1 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000338/2022-2023 | 991/CD | 29/09/2022 | 28/11/2022 | MS SSB CONSTRUCTION CO | 76.14 | 45.07 | 59.19 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC & other allied works at S. BHETAGURI ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000360/2022-2023 | 1013/CD | 29/09/2022 | 29/10/2022 | MALAY KR.DEB | 9.94 | 9.37 | 94.27 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC & other allied works at S. BHETAGURI ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000361/2022-2023 | 1014/CD | 29/09/2022 | 29/10/2022 | MS SSB CONSTRUCTION CO | 10.02 | 7.14 | 71.27 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC Repairing OHR supply of Specials & other allied works at SINGIMARI BHETAGURI ZONE ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000418/2022-2023 | 3276/CD | 02/12/2022 | 31/01/2023 | MALAY KR.DEB | 19.28 | 9.2 | 47.73 | 100
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC Repairing OHR supply of Specials & other allied works at SINGIMARI BHETAGURI ZONE - II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000419/2022-2023 | 3277/CD | 02/12/2022 | 31/01/2023 | MALAY KR.DEB | 19.18 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿B) at SINGIMARI BHETAGURI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000421/2021-2022 | 1519/CD | 15/03/2022 | 11/09/2022 | MS SSB CONSTRUCTION CO | 291.66 | 279.56 | 95.85 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Execution of different works related to S.BHETAGURI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000446/2022-2023 | 1423/CD | 29/12/2022 | 28/01/2023 | SIDHARTHA ROY | 9.98 | 9.98 | 100 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Execution of different works related to S.BHETAGURI Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000447/2022-2023 | 1424/CD | 29/12/2022 | 28/01/2023 | MALAY KR.DEB | 9.98 | 9.41 | 94.3 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC construction SSPost with soak pit & New UPVC/DI/GI Pipe line and other allied works (PART ¿A) at SINGIMARI BHETAGURI ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000462/2021-2022 | 1608/CD | 24/03/2022 | 22/07/2022 | MS DGB ENTERPRISE | 178.67 | 153.58 | 85.96 | 1
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿A) at SINGIMARI BHETAGURI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000463/2021-2022 | 1607/CD | 24/03/2022 | 22/07/2022 | JALPRABAHIKA PVT.LTD. | 260.39 | 208.26 | 79.98 | 33
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Singimari Bhetaguri Zone-I 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000512/2021-2022 | 1560/CD | 23/03/2022 | 07/04/2022 | MS SSB CONSTRUCTION CO | 2.98 | 2.98 | 100 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Singimari Bhetaguri Zone-I 4th Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000513/2021-2022 | 1561/CD | 23/03/2022 | 07/04/2022 | SWAPAN KUMAR ROY | 2.95 | 0 | 0 | 1
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of Switch Room, Boundary Wall at SINGIMARI PASCHIMPAR W.S.S under Cooch Behar Division P.H.E.Dte. PART A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000533/2021-2022 | 1633/CD | 29/03/2022 | 28/05/2022 | BIJOY ROY | 55.47 | 0 | 0 | 37
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-III) under JJM. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000869/2022-2023 | 1393/CD | 22/12/2022 | 01/01/2023 | SWAPAN KR.SARKAR | 0.92 | 0 | 0 | 100
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 488/CD | 07/07/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 167/CD | 27/04/2023 |  | Resource Division | 47.06 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1384/CD | 22/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2021-2022 | 1358/CD | 24/02/2022 |  | Resource Division | 10.98 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2021-2022 | 1593/CD | 24/03/2022 |  | Resource Division | 5.49 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | SOIL INVESTGATION DEWANHAT |  |  | VCH/000383/2022-2023 | BP-22-23-119 | 02/07/2022 |  | GEOCON INDIA | 1.22 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | FHTC |  |  | VCH/000384/2022-2023 | BP-22-23-117 | 02/07/2022 |  | GOUTAM KUMAR DAS | 1.86 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | PAYMENT OF ASHA KARMI RFEGARDING FTK |  |  | VCH/000939/2022-2023 | 431 | 22/11/2022 |  | MS DISTRICT MAZISTRATE COOCHBEHAR | 4.82 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | FHTC |  |  | VCH/001618/2021-2022 | BP_2021_22_442 | 11/03/2022 |  | MATARA CONSTRUCTION CO. | 40.24 | 0 | 0 | 0
32 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | COST OF PIPE |  |  | VCH/001697/2021-2022 | BP_2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 9.76 | 0 | 0 | 0
33 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Quotation for new service connection at Singimari Bhetaguri Z-I, TW No-III Application No- 4003022080 |  |  | BILL/00009/2022-2023 | BP-96/22-23 | 02/12/2022 |  | WBSEDCL | 0.7 | 0 | 0 | 0
34 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | QUOTATION FOR NEW SERVIVE CONNECTION AT SINGIMANI BHETAGURI TW NO-III,Z-II |  |  | BILL/00099/2023-2024 | BP-2023-24-37 | 10/05/2023 |  | WBSEDCL | 0.72 | 0 | 0 | 0
35 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery including other related accessories of Shingimari Bhetaguri Water Supply Scheme TW No.-I of Zone-I under NMD-II,PHE.Dte,CoochBehar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000663/2022-2023 | 499/CMSD | 15/07/2022 | 14/08/2022 | HARAGOURI ENTERPRISE | 1.73 | 1.73 | 100 | 0
36 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery including other related accessories of Shingimari Bhetaguri Water Supply Scheme TW No.-II of Zone-I under NMD-II,PHE.Dte,CoochBehar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000664/2022-2023 | 498/CMSD | 15/07/2022 | 14/08/2022 | CHOWDHURY AND BASU ENTERPRISE | 1.73 | 1.73 | 100 | 0
37 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Singimari Bhetaguri Water Supply Scheme Zone-I TW No.- III under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000698/2022-2023 | 1983/NMD-II | 07/12/2022 | 06/01/2023 | A.S. ENTERPRISE | 10.76 | 10.18 | 94.58 | 70
38 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Singimari Bhetaguri water supply scheme, TW no. III of Zone-II and under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000887/2022-2023 | 731/NMD-II | 30/03/2023 | 29/04/2023 | TAPAN BISWAS | 10.91 | 10.3 | 94.43 | 80
39 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001968/2023-2024 | 1012/CMSD | 31/10/2023 | 30/12/2023 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
40 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Singimari Bhetaguri piped water supply scheme. | SM/10149 | Augmentation | Quotation for new service connection for Singimari Bhetaguri, T/W no. III, Z-I, Application no. 4003022965 |  |  | VCH/001529/2022-2023 | null | 30/11/2022 |  | WBSEDCL | 0.7 | 0 | 0 | 0
Total | [13 empty] | 1419.28 | 853.22 | 60.12