## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for BALAKANDI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000005/2021-2022 | 129/CD | 06/07/2021 | 04/10/2021 | TAPASH DAS | 23.99 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC, laying new UPVC pipe line and Re- construction Cum Renovation of H/W site of boundary Wall & other allied works at in-connection with augmentation SOLMARI PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000025/2022-2023 | 41/CD | 07/04/2022 | 22/05/2022 | CHAKRABORTY ENTERPRISE. | 51.84 | 23.3 | 44.95 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC, Construction of 25 cum IEP pump house and laying of UPVC pipe line and other allied works at inconnection with augmentation SOULMARI PWSS under Cooch Behar Division, PHED.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000033/2022-2023 | 91/CD | 18/04/2022 | 07/04/2025 | MATRI ENTERPRISEES | 113.45 | 10.36 | 9.14 | 69
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Execution of different works related to SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000064/2023-2024 | 400/CD | 23/05/2023 | 22/06/2023 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 27.32 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Execution of different works related to SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000068/2023-2024 | 405/CD | 23/05/2023 | 22/06/2023 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 27.32 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC in-Connection with Repairing of OHR and Barricading of the existing OHR with plinth protection and other allied works at UPENCHOWKI KUCHLIBARI PWSS under Cooch Behar Division, P.H.E.Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000070/2022-2023 | 267/CD | 24/05/2022 | 08/07/2022 | SANJAY MANDAL | 19.68 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC, laying of Pipe line and other allied works at NALGRAM PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000074/2022-2023 | 271/CD | 24/05/2022 | 08/07/2022 | NABIN DEBNATH | 12.39 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Sinking of Big Dia Tubewell at 3rd Site of BARO SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000187/2022-2023 | 661/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 11.68 | 100 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Supply of C.I Specials for SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000247/2022-2023 | 738/CD | 27/08/2022 | 26/09/2022 | MS SSB CONSTRUCTION CO | 9.71 | 9.71 | 100 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Preparation of DPR for Augmentation of Soulmari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000304/2021-2022 | 1019/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.31 | 3.11 | 93.96 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing 140 nos F.H.T.C. Connection in the command area at MASALDANGA & Adjacent of Salmara P.W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000328/2021-2022 | 458/SD | 29/12/2021 | 13/01/2022 | MS BIDYUT SARKAR | 5 | 0 | 0 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC & other allied works at SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000359/2022-2023 | 1012/ CD | 29/09/2022 | 29/10/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 9.98 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Providing FHTC and Laying of Pipe line at SOULMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000404/2021-2022 | 1462/CD | 10/03/2022 | 09/04/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 21.41 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Re-construction of Boundary wall due to sinking of replacement tube well at 2nd site tube well (T/W-II) site under Soulmari PWSS under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000550/2021-2022 | 457/MTB | 04/03/2022 | 03/04/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 2.06 | 0 | 0 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Repairing and Maintenance of pump house & blower room at Soulmari PWSS under Mathabhanga Sub-Division, PHED. (Pump House-2, Blower room-1) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000568/2021-2022 | 458/MTB | 04/03/2022 | 11/03/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 3.19 | 3.12 | 97.88 | 1
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Execution of different works related to SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000773/2022-2023 | 1660/CD | 10/02/2023 | 11/04/2023 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 25.45 | 0 | 0 | 40
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1366/CD | 22/12/2022 | 22/12/2022 | Resource Division | 75.09 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1472/CD | 16/01/2023 | 16/01/2023 | Resource Division | 10.73 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | FHTC |  |  | VCH/000052/2022-2023 | BP_22_23_26 | 13/04/2022 | 13/04/2022 | SHREE RANI SATI ENTERPRISE | 13.22 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | FHTC |  |  | VCH/000055/2022-2023 | BP_22_23_29 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 16.77 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | FHTC |  |  | VCH/000056/2022-2023 | BP_22_23_34 | 13/04/2022 | 13/04/2022 | PARITOSH DUTTA | 22.12 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | FHTC |  |  | VCH/000106/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 1.08 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | SHIFTING OF P/LINE AT DHALPAL |  |  | VCH/000392/2022-2023 | BP-22-23-120 | 11/07/2022 | 11/07/2022 | GOUTAM KUMAR DAS | 20.89 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | FHTC |  |  | VCH/001621/2021-2022 | BP_2021_22_445 | 11/03/2022 | 11/03/2022 | CHAKRABORTY ENTERPRISE. | 31.57 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | PIPE |  |  | VCH/001707/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.8 | 0 | 0 | 0
26 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | QUOTATION FOR NSC AT SOULMARI PH NO-I |  |  | BILL/01816/2023-2024 | BP-2023-24-338 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.22 | 0 | 0 | 0
27 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | SM/10157 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Soulmari (Mekhliganj Block) Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001150/2023-2024 | 2903/NMD-II | 19/10/2023 | 18/11/2023 | ASHWIRBAD WOOD CRAFT | 10.53 | 0 | 0 | 100
Total | [13 empty] | 579.79 | 61.29 | 10.57