## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | FUEL BILL |  |  | BILL/02023/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 1.95 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | FUEL BILL |  |  | BILL/02077/2023-2024 | BP-1412 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 1.95 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Providing 150nos of F.H.T.C. for Haribhanga (Part-B) W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000118/2022-2023 | 217/SD | 27/06/2022 | 27/07/2022 | ANIMESH DHAR CHOUDHURY | 4.82 | 4.82 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Providing 150nos of F.H.T.C. for Haribhanga (Part-A) W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000119/2022-2023 | 216/SD | 27/06/2022 | 27/07/2022 | ANIMESH DHAR CHOUDHURY | 4.82 | 4.82 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Providing FHTC & other allied works at HARIBHANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000316/2022-2023 | 925/CD | 26/09/2022 | 26/10/2022 | ANIMESH DHAR CHOUDHURY | 9.99 | 9.98 | 99.96 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at HARIBHANGA W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000540/2021-2022 | 1640/CD | 29/03/2022 | 28/05/2022 | ANIMESH DHAR CHOUDHURY | 61.46 | 17.29 | 28.14 | 65
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 485/CD | 07/07/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2021-2022 | 1590/CD | 24/03/2022 |  | Resource Division | 5.5 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | FHTC HARIBHANGA |  |  | VCH/000410/2022-2023 | BP-22-23-142 | 26/07/2022 |  | ANIMESH DHAR CHOUDHURY | 22.3 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | SM/10160 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvination of Haribhanga water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000745/2023-2024 | 2313/NMD-II | 01/08/2023 | 31/08/2023 | UTTAM PAUL | 10.4 | 0 | 0 | 0
Total | [13 empty] | 19924.8 | 36.91 | 0.19