## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | FHTC AT SINGIMARI PASCHIMPAR PWSS |  |  | BILL/02069/2023-2024 | BP-1126 | 02/03/2024 |  | BIJOY ROY | 11.89 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of Singimari Paschimpar PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000026/2022-2023 | 42/CD | 07/04/2022 | 22/05/2022 | MS DD ENTERPRISE | 12.13 | 9.67 | 79.73 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | Name of Work: Execution of different works related to SINGIMARI PASCHIMPAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000415/2023-2024 | 1470/CD | 20/12/2023 | 18/02/2024 | SANKAR BANIK | 9.55 | 9.53 | 99.78 | 100
6 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT SINGIMARI PACHUNIRPAR (REJU) TW NO-III |  |  | BILL/00167/2023-2024 | BP-2023-24-120 | 18/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | SM/10362 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Singimari Paschimpar water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000684/2023-2024 | 2094/NMD-II | 26/07/2023 | 25/08/2023 | BLUE PINE | 11.06 | 5.22 | 47.18 | 80
Total | [13 empty] | 19890.63 | 24.42 | 0.12