## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BARO PINJARERJHAR Water Supply Scheme | SM/11258 | Augmentation | Execution of different works related to BARO PINJARERJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000026/2023-2024 | 384/CD | 23/05/2023 | 22/07/2023 | SUBHAS CHANDRA ROY | 52.75 | 12.76 | 24.2 | 44
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BARO PINJARERJHAR Water Supply Scheme | SM/11258 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BARO PINJARERJHAR Water Supply Scheme | SM/11258 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 231/CD | 27/04/2023 |  | Resource Division | 18.95 | 0 | 0 | 0
Total | [13 empty] | 19860.98 | 12.76 | 0.06