## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Preparation of DPR for Augmentation of BAJEJAMA CHILAKHANA (Zone-II) Piped Water Supply Scheme under TUFANGANJ Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000172/2022-2023 | 631/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.88 | 2.68 | 92.79 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART D) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000289/2022-2023 | 890/CD | 22/09/2022 | 22/10/2022 | M/S BADAL CH SAHA | 8.74 | 8.74 | 100 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Preparation of DPR for Augmentation of BARAKODALI Piped Water Supply Scheme under TUFANGANJ Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000290/2021-2022 | 1005/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.03 | 3.03 | 100 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART Z) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000290/2022-2023 | 891/CD | 22/09/2022 | 22/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART X) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000291/2022-2023 | 892/CD | 22/09/2022 | 22/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART M) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000292/2022-2023 | 893/CD | 22/09/2022 | 22/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART K) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000296/2022-2023 | 897/CD | 22/09/2022 | 22/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART R) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000298/2022-2023 | 899/CD | 22/09/2022 | 22/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Consultancy work in connection with Augmentation of different PWSS at Cooch Behar Division PHE Dte. under JAL JEEVAN MISSION (PART A) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000301/2022-2023 | 910/CD | 26/09/2022 | 26/10/2022 | BHAGWATI BHUJEL | 8.74 | 8.74 | 100 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Preparation of DPR for Augmentation of Santoshpur Piped Water Supply Scheme under Tufanganj Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000308/2021-2022 | 1023/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.96 | 2.96 | 100 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Preparation of Augmentation DPR for different Piped Water Supply Scheme under Cooch Behar Division, PHED | SM/11269 | Support-M&E | Preparation of DPR for Augmentation of Hemkumari Zone-I Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000808/2022-2023 | 853/CD | 19/09/2022 | 26/09/2022 | RADIANT | 0.99 | 0 | 0 | 0
Total | [13 empty] | 71.03 | 69.83 | 98.31