## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Execution of different works related to Baraibari A PWSS under JAL JEEVAN MISSION |  |  | ORD/000074/2024-2025 | 4002 | 18/06/2024 | 16/09/2024 | SHREE RANI SATI ENTERPRISE | 86.16 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Renovation of Laying Distribution System of pipe line Harinkuchi Swapna-Baromasia, Khanka & Dogarpar under PUTIA BAROMASIA PWSS under Cooch Behar Divn., PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000129/2020-2021 | 1386/CD | 07/01/2021 | 07/04/2021 | NABIN DEBNATH | 13.94 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Execution of different works related to PUTIA BAROMASIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000370/2023-2024 | 1389/CD | 05/12/2023 | 03/02/2024 | SIBAPADA SINGHA ROY | 32.43 | 3.45 | 10.63 | 21
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Execution of different works related to PUTIABARO MASIA ZONE 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1011/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000495/2022-2023 | 1560/CD | 24/01/2023 | 23/06/2023 | SHREE RANI SATI ENTERPRISE | 350.47 | 123.52 | 35.24 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Providing FHTC & other allied works in the command area of KISMAT DASGRAM PWSS under Cooch Behar Division, PHED |  |  | ORD/000509/2023-2024 | 306/CD | 09/02/2024 | 09/04/2024 | SHREE RANI SATI ENTERPRISE | 34.93 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Providing FHTC & other allied works at PUTIA BAROMASIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000511/2022-2023 | 1584/CD | 01/02/2023 | 03/03/2023 | SUBODH ROY & SONS | 9.97 | 9.96 | 99.96 | 100
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Putia Baramasia water supply scheme, TW no III of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar |  |  | ORD/000853/2023-2024 | 2439/NMD-II | 11/08/2023 | 10/09/2023 | MASSK ENGINEERING WORKS | 11.07 | 0 | 0 | 0
Total | [13 empty] | 20328.26 | 136.93 | 0.67