## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Execution of different works related to PAKHIHAGA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 988/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000468/2022-2023 | 1519/CD | 19/01/2023 | 18/06/2023 | AKANSHA COMMERCIAL PVT. LTD. | 396.75 | 233.01 | 58.73 | 70
3 | COOCHBEHAR | Dinhata - I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Execution of different works related to PAKHIHAGA PWSS under JAL JEEVAN MISSION DHT 1 |  |  | ORD/000478/2023-2024 | 281/CD | 09/02/2024 | 09/04/2024 | AKANSHA COMMERCIAL PVT. LTD. | 60.97 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 177/CD | 27/04/2023 |  | Resource Division | 20.95 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | QUOTATION FOR NSC AT PAKHIHAGA PH NI I |  |  | BILL/00524/2023-2024 | BP-2023-24-148 | 01/06/2023 |  | WBSEDCL | 1.11 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | QUOTATION FOR NSC AT PAKHIHAGA PH NO II |  |  | BILL/00525/2023-2024 | BP-2023-24-149 | 01/06/2023 |  | WBSEDCL | 1.11 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pakhihaga water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000665/2023-2024 | 2021/NMD-II | 26/07/2023 | 25/08/2023 | TAPAN BISWAS | 19.77 | 4.97 | 25.16 | 50
Total | [13 empty] | 20289.96 | 237.98 | 1.17