## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Execution of different works related to BIJLICHATKA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 976/1-5/NBC-1; DT: 19-01-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000455/2022-2023 | 1506/CD | 19/01/2023 | 18/06/2023 | GEETA CONSTRUCTION | 400.44 | 53.73 | 13.42 | 80
3 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 132/CD | 27/04/2023 |  | Resource Division | 22.41 | 0 | 0 | 0
4 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 89/CD | 11/01/2024 |  | Resource Division | 13.79 | 0 | 0 | 0
5 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BIJLICHATKA TW NO. I |  |  | BILL/02612/2023-2024 | BP-2023-24-575 | 01/02/2024 |  | WBSEDCL | 8.45 | 0 | 0 | null
6 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BIJLICHATKA TW NO. II. |  |  | BILL/02613/2023-2024 | BP-2023-24-576 | 01/02/2024 |  | WBSEDCL | 7.78 | 0 | 0 | null
7 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bijlichatka water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P,Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000847/2023-2024 | 2427/NMD-II | 10/08/2023 | 09/09/2023 | KARMAKAR CONSTRUCTION | 21.59 | 16.17 | 74.92 | 80
Total | [13 empty] | 20263.76 | 69.9 | 0.34