## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to AUG. SOULMARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000036/2024-2025 | 1137/CD | 14/06/2024 | 13/08/2024 | M/S A. B. ENTERPRISE | 0 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to AUG. SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000055/2024-2025 | 1269/CD | 02/07/2024 | 30/09/2024 | M/S A. B. ENTERPRISE | 39.89 | 0 | 0 | 30
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to RAKHALMARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000080/2024-2025 | 1188/CD | 18/06/2024 | 16/09/2024 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 32.46 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Preparation of DPR for Augmentation of SOULMARI (Zone-II) Piped Water Supply Scheme under COOCH BEHAR SADAR Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000168/2022-2023 | 627/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.69 | 2.69 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to BARO SOULMARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000556/2023-2024 | 654/CD | 11/03/2024 | 10/05/2024 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 51.5 | 0 | 0 | 30
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to SOULMARI Z 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1129/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000623/2022-2023 | 1691/CD | 13/02/2023 | 13/07/2023 | SWAPAN KUMAR ROY | 277.32 | 56.35 | 20.32 | 50
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000825/2022-2023 | 2045/CD | 31/03/2023 | 30/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 200/CD | 27/04/2023 |  | Resource Division | 19.66 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Soulmari (Dinhata-II) water supply scheme, TW no. I and II of Zone-Iand II under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/000827/2023-2024 | 2397/NMD-II | 09/08/2023 | 08/09/2023 | DAS ENTERPRISE | 41.51 | 0 | 0 | 0
Total | [13 empty] | 20255.3 | 60.02 | 0.3