## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | Supply of different Forms & Stationary Items for day to day Office work for the Office of the Executive Engineer, Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000054/2023-2024 | 267/CD | 28/04/2023 | 05/05/2023 | EASTERN MARKETING ENTERPRISE | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | Execution of different works related to UPENCHAUKIKUCHLIBARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1128/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000622/2022-2023 | 1873/CD | 14/03/2023 | 11/08/2023 | M/S. NITYAGOPAL BANIK | 203.87 | 38.71 | 18.99 | 38
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | Supply of different Forms & Stationary Items for day to day Office work for the Office of the Assistant Engineer, Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000741/2022-2023 | 1619/CD | 07/02/2023 | 14/02/2023 | EASTERN MARKETING ENTERPRISE | 0.45 | 0.45 | 100 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | REPARING OF XEROX MACHINE AND OTHER ALLIED WORKS UNDER COOCH BEHAR DIVISINAL OFFICE, PHED |  |  | VCH/000929/2022-2023 | 409 | 10/11/2022 |  | ELECTRO SERVICES PVT.LTD | 0.28 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | SINKING OF BIG DIA TUBE-WELL AT DIFFERENT PWSS UNDER COOCH BEHAR DIVISION, PHED |  |  | VCH/000935/2022-2023 | 412 | 10/11/2022 |  | GEOLOGIST SWID DISTRICT LEVEL GROUND WATER RESOURCE AUTHARITY | 0.28 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | FHTC AT UPENCHWKI KUCHLIBARI PWSS |  |  | VCH/001024/2022-2023 | 413 | 10/11/2022 |  | SANJAY MANDAL | 4.95 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | FHTC AND REP. OF OHR AT UPENCHOKI KUCHLIBARI PWSS |  |  | VCH/001026/2022-2023 | 415 | 10/11/2022 |  | SANJAY MANDAL | 18.68 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | SM/13227 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of UPENCHOUKI KUCHLIBARI water supply scheme, TW no-I Under JJM under Northern Mechanical Division-II, PHE Dte. |  |  | ORD/002040/2023-2024 | 1189/NMD-II | 11/03/2024 | 10/04/2024 | ASHWIRBAD WOOD CRAFT | 11 | 0 | 0 | 0
Total | [13 empty] | 20085.48 | 40.14 | 0.2