## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Execution of different works related to BARA MARICHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000477/2023-2024 | 279/CD | 09/02/2024 | 09/04/2024 | GOUTAM KUMAR DAS | 93.42 | 0 | 0 | 80
2 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Execution of different works related to BARA MARICHA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1293/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000606/2022-2023 | 1900/CD | 17/03/2023 | 14/08/2023 | UMEX POLYMERS PVT LTD | 367.91 | 149.59 | 40.66 | 25
3 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 70/CD | 11/01/2024 |  | Resource Division | 12.32 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | QUOTATION FOR NSC AT BARA MARICHA PH NO-I |  |  | BILL/01753/2023-2024 | BP-2023-24-355 | 03/10/2023 |  | WBSEDCL | 5.59 | 0 | 0 | 0
5 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | QUOTATION FOR NSC AT BARA MARICHA PH NO-II |  |  | BILL/01754/2023-2024 | BP-2023-24-356 | 27/09/2023 |  | WBSEDCL | 4.7 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bara Maricha Water Supply Scheme TW No.- I AND II under NMDII, PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001043/2023-2024 | 2692/NMD-II | 14/09/2023 | 14/10/2023 | M/S ANJALI ENTERPRISE | 20.05 | 0 | 0 | 0
Total | [13 empty] | 504 | 149.59 | 29.68