## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000362/2023-2024 | 1395/CD | 05/12/2023 | 03/02/2024 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 31.31 | 3.83 | 12.25 | 24
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000507/2022-2023 | 1231/CD. | 28/11/2022 | 28/12/2022 | COOCH BEHAR U/E CO-OP-LAB. CONT. & CONSTN. SO-LTD | 9.93 | 9.93 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Laying DI P/Line & other allied works related to STK Z I PWSS under JAL JEEVAN MISSION |  |  | ORD/000574/2023-2024 | 616/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 80.24 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000581/2023-2024 | 621/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 25.98 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1213/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000582/2022-2023 | 1772/CD | 02/03/2023 | 30/07/2023 | Z STAR COMMOTRADE PVT LTD | 645.95 | 310.58 | 48.08 | 49
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Laying DI P/Line & other allied works related to STK Z 1 PWSS under JAL JEEVAN MISSION |  |  | ORD/000590/2023-2024 | 627/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 95.68 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000778/2022-2023 | 1694/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 7.65 | 7.65 | 100 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 242/CD | 27/04/2023 |  | Resource Division | 31.32 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Sitalkhuchi water supply scheme, TW no I and II of Zone-I and TW I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.APD |  |  | ORD/000811/2023-2024 | 2388/NMD-II | 09/08/2023 | 08/09/2023 | QUAZI NOZRUL ISLAM | 41.63 | 0 | 0 | 0
Total | [13 empty] | 969.68 | 332 | 34.24