## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | exc. of difft. works at ghughumari pwss |  |  | BILL/00789/2023-2024 | BP-243 | 01/07/2023 |  | MS BIDYUT SARKAR | 30 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | exc. of difft. work at atpukhari pwss |  |  | BILL/00791/2023-2024 | BP-250-P2 | 04/07/2023 |  | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 29.8 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Execution of different works related to SANTOSHPUR ZONE-I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1010/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000496/2022-2023 | 1561/CD | 24/01/2023 | 23/06/2023 | UTPAL CHAKRABORTY | 265.78 | 117.91 | 44.37 | 50
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | New service connection charge at Santoshpur (Zone-I) PWSS, P/H-III. |  |  | BILL/00888/2024-2025 | BP-287/24-25 | 22/08/2024 |  | WBSEDCL | 5.86 | 0 | 0 | null
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of Santoshpur water supply scheme, TW no III of Zone-I and TW No-III of Zone-II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000821/2023-2024 | 2399/NMD-II | 09/08/2023 | 08/09/2023 | P K ENGINEERING | 20.78 | 8.63 | 41.53 | 50
Total | [13 empty] | 20141.51 | 126.54 | 0.63