## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Execution of different works related to BALASI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1346/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000615/2022-2023 | 1965/CD | 24/03/2023 | 21/08/2023 | GHOSH AND SAHA CONSTRUCTION | 547.55 | 240.89 | 43.99 | 50
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1343/CD | 19/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 178/CD | 27/04/2023 |  | Resource Division | 44.89 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 82/CD | 11/01/2024 |  | Resource Division | 15.46 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALASHI PWSS PH NO-II |  |  | BILL/00082/2023-2024 | BP-2023-24-77 | 15/05/2023 |  | WBSEDCL | 0.93 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BALASI TW I. |  |  | BILL/00519/2024-2025 | BP-122/24-25 | 24/05/2024 |  | WBSEDCL | 6.55 | 0 | 0 | null
8 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for of Balasi water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000681/2023-2024 | 2127/NMD-II | 27/07/2023 | 26/08/2023 | SUBODH KUMAR BANIK | 22.03 | 0 | 0 | 0
Total | [13 empty] | 20488.29 | 240.89 | 1.18