## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Execution of different works related to MAINAGURI DIGHALHATI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 982/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000462/2022-2023 | 1513/CD | 19/01/2023 | 18/06/2023 | S DUTTA | 489.9 | 203.08 | 41.45 | 60
3 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Gap filling between pipe line related to Bhogdabri & M DIGHALHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000546/2023-2024 | 650/CD | 11/03/2024 | 10/05/2024 | M/S MAA MANASA CONSTRUCTION CO. | 17.68 | 0 | 0 | 35
4 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 96/CD | 26/04/2023 |  | Resource Division | 16.87 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | ADDITIONAL QUOTATION FOR ELECTRICAL INFRA. DEV. WORK AT MAINAGURI DIGHALHATI. |  |  | BILL/00818/2024-2025 | BP-246/24-25 | 30/07/2024 |  | WBSEDCL | 3.5 | 0 | 0 | null
6 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | QUOTATION FOR NSC AT MAYANAGURI DIGHALHATI TW NO-II |  |  | BILL/01794/2023-2024 | BP-2023-24-309 | 27/09/2023 |  | WBSEDCL | 8.21 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | QUOTATION FOR NSC AT MAYANAGURI DIGHALHATI TW NO-I |  |  | BILL/01795/2023-2024 | BP-2023-24-308 | 27/09/2023 |  | WBSEDCL | 5.14 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Mainaguri Dighalhati water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000759/2023-2024 | 2338/NMD-II | 01/08/2023 | 31/08/2023 | THE BANERJEE CONCERN | 22.1 | 0 | 0 | 60
Total | [13 empty] | 20352.69 | 203.08 | 1