## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | New service connection charge at Nigamnagar (Zone-II) pwss, P/H-II in the dist of Coochbehar |  |  | BILL/00199/2024-2025 | null | 21/06/2024 |  | WBSEDCL | 16.22 | 0 | 0 | null
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Repairing & Renovation of existing civil construction and formation of water testing laboratory for Aug. of Nigamnagar PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000023/2023-2024 | 387/CD | 23/05/2023 | 20/10/2023 | BIJOY ROY | 26.81 | 3.88 | 14.47 | 42
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Land Scaping & beautification of garden at Nigamnagar & Lab cun Rest Shed under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000322/2023-2024 | 1305/CD | 24/11/2023 | 23/01/2024 | DAS ENTERPRISE | 4.71 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to PNIGAMNAGAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000360/2023-2024 | 1344/CD | 24/11/2023 | 23/01/2024 | BIJOY ROY | 12.25 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to NAHARHAT BANDAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000393/2023-2024 | 1365/CD | 05/12/2023 | 03/02/2024 | GHOSH AND SAHA CONSTRUCTION | 66.79 | 0 | 0 | 30
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to NIGAMNAGAR Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000436/2022-2023 | 1413/CD | 29/12/2022 | 28/01/2023 | UNIQUE UNEMPLOYED ENGINEER CO -OPARATIVE SOCIETY LTD. | 9.57 | 8.34 | 87.11 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to NIGAMNAGAR Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000437/2022-2023 | 1414/CD | 29/12/2022 | 28/01/2023 | SARKAR CONSTRUCTION | 9.57 | 9.57 | 100 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to AUG. of NIGAMNAGAR ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1012/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000494/2022-2023 | 1559/CD | 24/01/2023 | 23/06/2023 | TAPAN CHANDA | 430.06 | 0 | 0 | 38
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to AUG. of NIGAMNAGAR ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1215/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000527/2022-2023 | 1777/CD | 02/03/2023 | 30/07/2023 | TAPAN CHANDA | 807.86 | 0 | 0 | 46
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to AUG. NIGAMNAGAR ZONE - III PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1216/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000533/2022-2023 | 1778/CD | 02/03/2023 | 30/07/2023 | TAPAN CHANDA | 604.28 | 0 | 0 | 46
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Execution of different works related to NIGAMNAGAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2022-2023 | 1693/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 7.64 | 7.64 | 100 | 100
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-K) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000817/2022-2023 | 1973/CD W | 24/03/2023 | 31/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000821/2022-2023 | 1998/CD | 28/03/2023 | 27/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-I) under JJM. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000867/2022-2023 | 1361/CD | 22/12/2022 | 01/01/2023 | SWAPAN KR.SARKAR | 0.92 | 0 | 0 | 100
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-II) under JJM. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000868/2022-2023 | 1392/CD | 22/12/2022 | 01/01/2023 | SWAPAN KR.SARKAR | 0.92 | 0 | 0 | 100
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 195/CD | 27/04/2023 |  | Resource Division | 29.54 | 0 | 0 | 0
18 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | QUOTATION FOR NSC AT NIGAMNAGAR Z-I PH NO-I |  |  | BILL/01815/2023-2024 | BP-2023-24-339 | 27/09/2023 |  | WBSEDCL | 4.94 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | New service connection at Nigamnagar PWSS(Zone-II), P/H-II |  |  | BILL/02421/2023-2024 | BP-2023-24-573 | 01/02/2024 |  | WBSEDCL | 7.07 | 0 | 0 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Charges for new service quotation at P/H-I under Nigamnagar PWSS, (Zone-III) in the district of Coochbehar. |  |  | BILL/02491/2023-2024 | BP-2023-24-570 | 30/01/2024 |  | WBSEDCL | 5.5 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Charges for new service connection at Nigamnagar (Zone-II) PWSS, P/H-I |  |  | BILL/02492/2023-2024 | BP-2023-24-569 | 30/01/2024 |  | WBSEDCL | 3.5 | 0 | 0 | 0
22 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | SM/13402 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGUMENTATION OF NIGAMNAGAR Water Supply Scheme TW No.- I and II OF ZONE -I TW No.- I and II OF ZONE -II TW No.- I and II OF ZONE -III under NMD-II,PHE.Dte,,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000664/2023-2024 | 1995/NMD-II | 25/07/2023 | 24/08/2023 | DEY ENTERPRISE (BALLY) | 65.42 | 0 | 0 | 20
Total | [13 empty] | 21904.81 | 31.4 | 0.14