## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Execution of different works related to BHANGRI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 979/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000459/2022-2023 | 1510/CD | 19/01/2023 | 18/06/2023 | M/S. DUTTA AND CO | 453.21 | 347.24 | 76.62 | 30
3 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part G | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000584/2023-2024 | 600/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 54.64 | 0 | 0 | 100
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1535/CD | 16/08/2024 |  | Resource Division | 29.4 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 154/CD | 27/04/2023 |  | Resource Division | 40.38 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 76/CD | 11/01/2024 |  | Resource Division | 15.81 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | QUOTATION FOR NSC AT BHAGNI PRATHAM KHANDA TW NO-I |  |  | BILL/01791/2023-2024 | BP-2023-24-351 | 27/09/2023 |  | WBSEDCL | 7.62 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | QUOTATION FOR NSC AT BHAGNI PRATHAM KHANDA TW NO-II |  |  | BILL/01792/2023-2024 | BP-2023-24-352 | 27/09/2023 |  | WBSEDCL | 4.36 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHANGRI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13461 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhangri Pratham Khanda water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000732/2023-2024 | 2322/NMD-II | 01/08/2023 | 31/08/2023 | DIAMOND ELECTRICAL WORKS | 20.99 | 9.74 | 46.37 | 40
Total | [13 empty] | 20415.7 | 356.97 | 1.75