## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | FHTC AT GORBHANGA PWSS |  |  | BILL/01215/2023-2024 | BP-732-P2 | 08/11/2023 |  | SUPER TECH ENGINEERS CO- OPERATIVE SPOCY.LTD | 30.09 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Execution of different works related to PUTIMARI BAKSHIBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000339/2023-2024 | 1323/CD | 24/11/2023 | 23/01/2024 | NABIN DEBNATH | 31.07 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Execution of different works related to PUTIMARI BAKSIBAS PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 978/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000458/2022-2023 | 1509/CD | 19/01/2023 | 18/06/2023 | NABIN DEBNATH | 396.56 | 248.46 | 62.65 | 75
6 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 140/CD | 27/04/2023 |  | Resource Division | 16.77 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Northern Mechanical Division II | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | QUOTATION FOR NSC AT PUTIMARI BAKSHIBASH TW NO I |  |  | BILL/01733/2023-2024 | BP-2023-24-328 | 27/09/2023 |  | WBSEDCL | 5.47 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar - II,Mathabhanga - II | Northern Mechanical Division II | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Puttimari Baksibas water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001085/2023-2024 | 2781/NMD-II | 05/10/2023 | 04/11/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.49 | 0 | 0 | 30
Total | [13 empty] | 20335.28 | 248.46 | 1.22