## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Execution of different works related to BARAIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000041/2023-2024 | 436/CD | 31/05/2023 | 28/10/2023 | ASHIM KUMAR CHAKRABORTY | 320.13 | 59.87 | 18.7 | 60
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Execution of different works related to BARAIBARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000087/2024-2025 | 1191/CD | 25/06/2024 | 23/09/2024 | ASHIM KUMAR CHAKRABORTY | 97.02 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000202/2023-2024 | 525/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000203/2023-2024 | 526/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Cooch Behar-I Block (Part -B) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000237/2023-2024 | 900/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Cooch Behar-II Block (Part -A) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000238/2023-2024 | 901/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Dinhata-I Block (Part-B) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000241/2023-2024 | 904/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Tufanganj-I Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000244/2023-2024 | 907/CD | 31/08/2023 | 23/11/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Tufanganj-II Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000245/2023-2024 | 908/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Providing House connection for BARAIBARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000336/2021-2022 | 1237/CD | 09/02/2022 | 01/03/2022 | M/S. MANDAL CONSTRUCTION | 7.02 | 7.02 | 100 | 1
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Providing FHTC & other allied works at BARAIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000424/2022-2023 | 1329/CD | 16/12/2022 | 14/02/2023 | M/S. MANDAL CONSTRUCTION | 20.38 | 20.37 | 99.98 | 1
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1345/CD | 19/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | QUOTATION FOR NSC AT BARAIBARI AUG PH NO -I |  |  | BILL/01819/2023-2024 | BP-2023-24-377 | 27/09/2023 |  | WBSEDCL | 5.53 | 0 | 0 | 0
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | NEW SERVICE CONNECTION AT BARAIBARI (AUG) PWSS, PH-II |  |  | BILL/03031/2023-2024 | BP-2023-24-685 | 14/03/2024 |  | WBSEDCL | 12.14 | 0 | 0 | null
15 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13860 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Baraibari Water Supply Scheme TW No.I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001081/2023-2024 | 2778/NMD-II | 05/10/2023 | 04/11/2023 | S.K ENTERPRISE | 11.5 | 0 | 0 | 60
Total | [13 empty] | 542.19 | 94.14 | 17.36