## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Execution of different works related to JHINGAPUNI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1001/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000485/2022-2023 | 1550/CD | 24/01/2023 | 23/06/2023 | MATRI ENTERPRISEES | 266 | 130.82 | 49.18 | 55
3 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JHINGAPUNNI PWSS TW NO -II |  |  | BILL/01427/2023-2024 | BP-2023-24-275 | 18/08/2023 |  | WBSEDCL | 6.96 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JHINGAPUNNI PWSS TW NO -I |  |  | BILL/01429/2023-2024 | BP-2023-24-281 | 18/08/2023 |  | WBSEDCL | 5.32 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jhingapuni water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000716/2023-2024 | 2100/NMD-II | 26/07/2023 | 25/08/2023 | HARAGOURI ENTERPRISE | 18.49 | 6.58 | 35.6 | 80
Total | [13 empty] | 20086.07 | 137.4 | 0.68