## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | FHTC AT NIJTARAF PWSS |  |  | BILL/00570/2023-2024 | BP-57-P | 19/04/2023 |  | ABHIJIT KUMAR DAS | 4.68 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | FHTC AT MORADANGA PWSS |  |  | BILL/00624/2022-2023 | BP-706-22-23-P1 | 27/02/2023 |  | KAJAL KUMAR DE | 0 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | New Laying of Balance portion HDPE Pipe line, Providing FHTC & Other allied work related to pipe line at MARADANGA WSS under Tufanganj Sub- Division, Cooch Behar Divn., P.H.E Dte. Under JJM Programme. Part A | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000033/2023-2024 | 370/CD | 23/05/2023 | 22/07/2023 | SHREE RANI SATI ENTERPRISE | 75.71 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | New Laying of Balance Pipe line, Providing FHTC Construction TW, PH, BW & Other allied work related to pipe line at MARADANGA WSS under Tufanganj Sub- Division, Cooch Behar Divn., P.H.E Dte. Under JJM Programme. Part B | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000034/2023-2024 | 371/CD | 23/05/2023 | 22/07/2023 | SHREE RANI SATI ENTERPRISE | 78.48 | 0 | 0 | 30
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC ,New laying UPVC Pipe, fully damaged due to PWD Construction with other allied work related to pipe line at CHHATOA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000205/2022-2023 | 680/CD | 23/08/2022 | 22/10/2022 | AASHIRBAD ENTERPRISE | 41.96 | 41.15 | 98.05 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC, new construction of boundary wall 2nd site and construction of rising main & with other allied work related to pipe line at Maradanga PWSS under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000265/2022-2023 | 208/TFG | 05/07/2022 | 04/08/2022 | KAJAL KUMAR DE | 3.91 | 3.83 | 97.97 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing House connection for MARADANGA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000347/2021-2022 | 1248/CD | 09/02/2022 | 01/03/2022 | KAJAL KUMAR DE | 8.77 | 8.77 | 100 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Construction P.House 3rd Site & B/Wall & Providing FHTC New Pipe line & other allied works at CHHATOA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000381/2021-2022 | 1293/CD | 15/02/2022 | 16/05/2022 | M/S BADAL CH SAHA | 47.65 | 18.82 | 39.49 | 100
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at MORADANGA ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000429/2022-2023 | 1331/CD | 19/12/2022 | 17/06/2023 | DILIP MAHATO | 125.4 | 103.94 | 82.89 | 99
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC Construction of 550 cum OHR and Laying of Pipe line Construction of Pump House & B/Wall at HWS Sinking of Tubewell at MORADANGA ZONE ¿ I PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000430/2022-2023 | 1332/CD | 19/12/2022 | 17/06/2023 | SHREE RANI SATI ENTERPRISE | 277.03 | 110.47 | 39.88 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC Construction of 300 cum OHR and Laying of Pipe line at MORADANGA ZONE ¿ I I PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000431/2022-2023 | 1333/CD | 19/12/2022 | 17/06/2023 | Z STAR COMMOTRADE PVT LTD | 139.53 | 87.05 | 62.39 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC Construction of Pump House & B/Wall Sinking of Tubewell and Laying of Pipe line at HW Site of MORADANGA ZONE ¿ I I PWSS under JAL JEEVAN MISSION (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000432/2022-2023 | 1334/CD | 19/12/2022 | 18/04/2023 | SHREE RANI SATI ENTERPRISE | 220.74 | 146.9 | 66.55 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at MORADANGA ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿C) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000433/2022-2023 | 1335/CD | 19/12/2022 | 02/02/2023 | SAMBHU BANIK | 101.76 | 99.87 | 98.14 | 45
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at MORADANGA ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000434/2022-2023 | 1337/CD | 19/12/2022 | 02/02/2023 | KAJAL KUMAR DE | 100.77 | 99.2 | 98.44 | 1
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of CHHATOA PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000505/2021-2022 | 1453/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 10.35 | 96.71 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000828/2022-2023 | 2048/CD | 31/03/2023 | 30/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 147/CD | 27/04/2023 |  | Resource Division | 95.84 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT MARADANGA (AUG) Z-I |  |  | BILL/00141/2023-2024 | BP-2023-24-119 | 18/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT MARADANGA (AUG) Z-II |  |  | BILL/00142/2023-2024 | BP-2023-24-118 | 18/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of MARADANGA Piped Water Supply Scheme | SM/14112 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augmentation of Maradanga water supply scheme, TW no I of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000672/2023-2024 | 2030/NMD-II | 26/07/2023 | 25/08/2023 | B.B CONCERNED | 30.35 | 24.94 | 82.2 | 60
Total | [13 empty] | 21155.58 | 756.28 | 3.57