## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | FHTC AT MAHISCHURA PWSS |  |  | BILL/01212/2023-2024 | BP-726-P1 | 08/11/2023 | 08/11/2023 | JAL PRAVAHIKA PVT. LTD. | 30.38 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Execution of different works with in CHANDAN CHOWRA & KAMINIRGHAT area related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION PART B | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000077/2024-2025 | 1712/CD | 25/09/2024 | 24/12/2024 | RAJAT ROY | 23.43 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Execution of different works related to CHANDAN CHOWRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000378/2023-2024 | 1361/CD | 05/12/2023 | 03/02/2024 | M/S A. B. ENTERPRISE | 48.37 | 46.44 | 96.02 | 96
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Execution of different works related to CHANDAN CHOWRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000481/2023-2024 | 280/CD | 09/02/2024 | 03/02/2025 | KRISHCHAK TRADING PRIVATE LIMITED | 31.4 | 7.46 | 23.75 | 40
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Execution of different works related to (Matikata area) CHANDAN CHOWRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000493/2023-2024 | 295/CD | 09/02/2024 | 05/04/2025 | SANKAR BANIK | 53.86 | 50.14 | 93.09 | 46
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Execution of different works related to CHANDAN CHOWRA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1234/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000563/2022-2023 | 1789/CD | 02/03/2023 | 24/07/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 912.78 | 629.1 | 68.92 | 60
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) |  | Junior Engineer, Head Quarter | ORD/000616/2023-2024 | 674/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) |  | Junior Engineer, Head Quarter | ORD/000617/2023-2024 | 675/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) |  | Junior Engineer, Head Quarter | ORD/000618/2023-2024 | 676/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
12 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) Under CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000619/2023-2024 | 677/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
13 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) Under CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000620/2023-2024 | 678/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
14 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) Under CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000621/2023-2024 | 679/CD | 11/03/2024 | 11/05/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
15 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 127/CD | 27/04/2023 | 27/04/2023 | Resource Division | 56.94 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 24/CD | 05/01/2024 | 05/01/2024 | Resource Division | 23.01 | 0 | 0 | 0
17 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | NEW SERVICE CONNECTION AT CHANDAN CHOWRA PWSS PH NO -I |  |  | BILL/00762/2024-2025 | BP-226/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 14.78 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | NEW SERVICE CONNECTION AT CHANDAN CHOWRA PWSS PH-II |  |  | BILL/00763/2024-2025 | BP-227/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 8.95 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | NEW SERVICE CONNECTION AT CHANDAN CHOWRA PWSS, PH-III |  |  | BILL/00894/2024-2025 | BP-329/24-25 | 03/10/2024 | 03/10/2024 | WBSEDCL | 11.37 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHANDAN CHOWRA PIPED WATER SUPPLY SCHEME | SM/14134 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
Total | [13 empty] | 21573.96 | 738.96 | 3.43