## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | EXECUTION OF DIFFERENT WORK AT KHARI ANALDORA PWSS |  |  | BILL/02015/2023-2024 | BP-1402 | 31/03/2024 |  | GHOSH AND SAHA CONSTRUCTION | 10.64 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHANDRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000348/2023-2024 | 1332/CD | 24/11/2023 | 23/01/2024 | GHOSH AND SAHA CONSTRUCTION | 5.29 | 0 | 0 | 30
4 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHONDRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000471/2023-2024 | 273/CD | 09/02/2024 | 09/04/2024 | GHOSH AND SAHA CONSTRUCTION | 94.82 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHONDRA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1231/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000550/2022-2023 | 1786/CD | 02/03/2023 | 30/07/2023 | GHOSH AND SAHA CONSTRUCTION | 649.01 | 501.82 | 77.32 | 85
6 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part E | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000582/2023-2024 | 599/CD | 11/03/2024 | 09/06/2024 | LIMRA SOCIAL WELFARE SOCIETY | 25.98 | 0 | 0 | 100
7 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 66/CD | 11/01/2024 |  | Resource Division | 17.2 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | QUOTATION FOR NSC AT KHARIJA ANALDHONDRA TW NO-II |  |  | BILL/01797/2023-2024 | BP-2023-24-311 | 27/09/2023 |  | WBSEDCL | 16.49 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | QUOTATION FOR NSC AT KHARIJA ANALDHONDRA TW NO-I |  |  | BILL/01799/2023-2024 | BP-2023-24-310 | 27/09/2023 |  | WBSEDCL | 7.97 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Khari Analdhondra Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001149/2023-2024 | 2901/NMD-II | 19/10/2023 | 18/11/2023 | M/S SAJAHAN CHOWDHURY | 21.45 | 7.39 | 34.44 | 100
Total | [13 empty] | 20638.15 | 509.2 | 2.47