## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Execution of different works related to UNISH BISHA PWSS under JAL JEEVAN MISSION |  |  | ORD/000494/2023-2024 | 296/CD | 09/02/2024 | 09/04/2024 | UNIVERSAL CONSTRUCTION | 78.77 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Execution of different works related to UNISH BASA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1235/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000551/2022-2023 | 1787/CD | 02/03/2023 | 30/07/2023 | M/S KAMAK ENGINEERS AND CO | 645.73 | 317.05 | 49.1 | 40
4 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part I | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000587/2023-2024 | 624/CD | 11/03/2024 | 10/05/2024 | RHYNO INFRASTRUCTURE | 99.34 | 0 | 0 | 100
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 15/CD | 05/01/2024 |  | Resource Division | 20.71 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | QUOTATION FOR NEW SERVICE CONNECTION AT UNISHBISHA TW NO -I |  |  | BILL/00089/2023-2024 | BP-2023-24-76 | 15/05/2023 |  | WBSEDCL | 0.93 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | QUOTATION FOR NEW SERVICE CONNECTION AT UNISHBISHA TW NO -II |  |  | BILL/00090/2023-2024 | BP-2023-24-83 | 15/05/2023 |  | WBSEDCL | 1.05 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for UNISH BASA (Mathabhanga-II Block) water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000707/2023-2024 | 2225/NMD-II | 28/07/2023 | 27/08/2023 | SARKAR ELECTRIC | 32 | 13.29 | 41.54 | 40
Total | [13 empty] | 20667.82 | 330.34 | 1.6