## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Providing House connection for GAJENDRAPUR CHOWRANGEE PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000015/2022-2023 | 31/CD | 07/04/2022 | 22/05/2022 | NORTHE BENGAL CONST CO | 6.45 | 5.82 | 90.25 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Execution of different works related to HALDIBARI BLOCK AND GAJENDRAPUR CHOWRINGHEE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000045/2024-2025 | 1153/CD | 14/06/2024 | 13/08/2024 | AASHIRBAD ENTERPRISE | 65.7 | 0 | 0 | 30
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Providing functional house hold tap connection within command area of GAJENDRAPUR CHOWRANGEE Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000149/2022-2023 | 214/MTB | 26/07/2022 | 10/08/2022 | NORTHE BENGAL CONST CO | 4.79 | 4.78 | 99.89 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Name of Work: Execution of different works related to DEBOTTAR BAKSHIGANJ PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000271/2023-2024 | 1039/CD | 22/09/2023 | 21/11/2023 | DAS ENTERPRISE | 22.67 | 8.32 | 36.71 | 74
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Laying of pipe line & construction of supporting pillar from Santi nagar to Gajendrapur Chowrangee due to widening of PWD Rd. under Tista Bridge fund at Gajendrapur PWSS under Cooch Behar Division, PHE Dte. |  |  | ORD/000280/2020-2021 | 669/CD | 14/08/2020 | 12/11/2020 | NORTHE BENGAL CONST CO | 10.41 | 3.8 | 36.49 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Execution of different works related to PMAJUMDER & G CHOWRANGEE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000550/2023-2024 | 608/CD | 11/03/2024 | 10/05/2024 | SHRI ANNAPURNA DISTRIBUTORS | 84.76 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Execution of different works related to GAJENDRAPUR CHOWRANGEE PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1116/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000604/2022-2023 | 1854/CD | 14/03/2023 | 11/08/2023 | M/S TORSHA CONSTRUCTION | 314.01 | 0.09 | 0.03 | 12
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Construction of 500 cum OHR and Laying distrbution System and other allied works Gajendrapur Chowrangee Piped Water Supply Scheme at Haldibari Block for DistrictCoochbehar under Coochbehar Division of North Bengal Circle-I,PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000776/2023-2024 | 659/CD | 11/03/2024 | 05/01/2025 | TORSHA CONSTRUCTION | 321 | 0 | 0 | 30
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 192/CD | 27/04/2023 |  | Resource Division | 133.01 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Electric Quotation Bill for NSC at GAJENDRAPUR CHOWRANGEE (AUG TW-III) |  |  | BILL/02237/2023-2024 | BP-2023-24-571 | 01/02/2024 |  | WBSEDCL | 7.39 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/14933 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augmentation of GAJENDRAPUR CHOWRANGEE water supply scheme, TW no I under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000799/2023-2024 | 2378/NMD-II | 09/08/2023 | 08/09/2023 | S.D CONCERN WORKSHOP | 10.94 | 0 | 0 | 0
Total | [13 empty] | 20770.41 | 22.81 | 0.11