## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Execution of different works related to BHALKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000223/2023-2024 | 397/CD. | 23/05/2023 | 20/10/2023 | NABIN DEBNATH | 361.86 | 220.65 | 60.98 | 75
2 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Execution of different works related to BHALKA area related to Baro Soulmari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000301/2023-2024 | 1055/CD | 22/09/2023 | 21/11/2023 | NABIN DEBNATH | 41.27 | 32.41 | 78.53 | 79
3 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 155/CD | 27/04/2023 |  | Resource Division | 10.62 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BHALKA PWSS TW NO -II |  |  | BILL/01423/2023-2024 | BP-2023-24-279 | 18/08/2023 |  | WBSEDCL | 1.99 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BHALKA PWSS TW NO -I |  |  | BILL/01425/2023-2024 | BP-2023-24-278 | 18/08/2023 |  | WBSEDCL | 4.27 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bhalka Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001049/2023-2024 | 2699/NMD-II | 15/09/2023 | 15/10/2023 | TAPAN BISWAS | 20.11 | 9.71 | 48.26 | 80
Total | [13 empty] | 20229.41 | 262.76 | 1.3