## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Execution of different works related to BRAHMOTTAR CHATRA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1286/1-5/NBC-1; Dt.: 17-03-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000620/2022-2023 | 1904/CD | 17/03/2023 | 14/08/2023 | AMBITIOUS ENTERPRISE | 433.2 | 182.38 | 42.1 | 25
3 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BRAHMOTTAR CHATRA TW NO. II |  |  | BILL/02615/2023-2024 | BP-2023-24-578 | 01/02/2024 |  | WBSEDCL | 12.46 | 0 | 0 | null
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BRAHMOTTAR CHATRA TW NO. I |  |  | BILL/02617/2023-2024 | BP-2023-24-579 | 01/02/2024 |  | WBSEDCL | 7.47 | 0 | 0 | null
5 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Brahmottar Chatra water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/001009/2023-2024 | 2591/NMD-II | 24/08/2023 | 23/09/2023 | M/S P.P ELECTRICALS | 21.3 | 0 | 0 | 0
Total | [13 empty] | 20263.72 | 182.38 | 0.9