## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Execution of different works related to KHARIKABARI PWSS under JAL JEEVAN MISSION PART D1 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000050/2024-2025 | 1265/CD | 02/07/2024 | 30/09/2024 | M/S A. B. ENTERPRISE | 35.1 | 0 | 0 | 35
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Execution of different works related to KHARIKABARI PWSS under JAL JEEVAN MISSION PART D2 |  |  | ORD/000051/2024-2025 | 1266/CD | 02/07/2024 | 30/09/2024 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 35.09 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Providing functional house hold tap connection within command area under KHARIKABARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000134/2022-2023 | 122/MTB | 23/06/2022 | 08/07/2022 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 4.78 | 4.78 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Providing FHTC and Laying of pipe line, Const. Of Pump house , B/Wall at 3rd T/W site and other allied work of KHARIKABARI PWSS under JAL JEEVAN MISSION (PART -A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000185/2022-2023 | 1822/CD | 06/03/2023 | 05/05/2023 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 97.02 | 59.95 | 61.8 | 50
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Execution of different works related to KHARIKABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000330/2023-2024 | 1313/CD | 24/11/2023 | 23/01/2024 | MS DD ENTERPRISE | 9.06 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Execution of different works related to KHARIKABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000336/2023-2024 | 1320/CD | 24/11/2023 | 23/01/2024 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 60.94 | 0 | 0 | 67
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Execution of different works related to (SALMARA PKHANDA area) KHARIKABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000511/2023-2024 | 308/CD | 09/02/2024 | 09/04/2024 | M/S SURAJIT MAJUMDER | 9.69 | 3.7 | 38.16 | 77
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 1957/CD | 24/03/2023 |  | Resource Division | 149.45 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | SM/15932 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Kharikabari Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000924/2023-2024 | 2504/NMD-II | 14/08/2023 | 13/09/2023 | SAIKAT SINHA | 9.86 | 3.81 | 38.65 | 30
Total | [13 empty] | 411 | 72.24 | 17.58