## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Execution of different works related to JIRANPUR PWSS under JAL JEEVAN MISSION P B |  |  | ORD/000071/2024-2025 | 1184/CD | 18/06/2024 | 16/09/2024 | MALAY KR.DEB | 66.85 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Execution of different works related to AUG. of HARINCHAOWRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000815/2022-2023 | 1997 | 28/03/2023 | 01/03/2024 | MATRI ENTERPRISEES | 272.18 | 29.72 | 10.92 | 40
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 107/CD | 26/04/2023 |  | Resource Division | 29.03 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | NEW SERVICE CONNECTION CHARGES AT HARIN CHOWRA (AUG) PWSS, PH-I |  |  | BILL/00197/2024-2025 | BP-52/24-25 | 29/04/2024 |  | WBSEDCL | 6.12 | 0 | 0 | null
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Harinchowra Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001100/2023-2024 | 2833/NMD-II | 12/10/2023 | 11/11/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.5 | 0 | 0 | 30
Total | [13 empty] | 20181.98 | 29.72 | 0.15