## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | FUEL BILL |  |  | BILL/02018/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 3.88 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | FUEL BILL |  |  | BILL/02075/2023-2024 | BP-1407 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 3.88 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000084/2023-2024 | 619/CD | 12/07/2023 | 09/12/2023 | GOUTAM KUMAR DAS | 329.26 | 14.54 | 4.42 | 60
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Constructions of 250 Cum OHR as per Departmental Design & drawing , Providing F.H.T.C ,New laying DI Pipe Line & other allied work at CHHAT RAMPUR PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000217/2022-2023 | 706/CD | 27/08/2022 | 23/02/2023 | GOUTAM KUMAR DAS | 88.74 | 30.43 | 34.29 | 0.5
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000748/2022-2023 | 1832/CD | 09/03/2023 | 08/04/2023 | GOUTAM KUMAR DAS | 61.23 | 46.43 | 75.84 | 18
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT, TW No.-I under NMD-II PHE DTE,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000929/2023-2024 | 2526/NMD-II | 16/08/2023 | 15/09/2023 | M/S A.D. ENTERPRISE | 10.58 | 4.39 | 41.54 | 50
Total | [13 empty] | 607.4 | 95.8 | 15.77