## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | FUEL BILL |  |  | BILL/02022/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 1.74 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | fuel bill |  |  | BILL/02049/2023-2024 | BP-1411 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 1.74 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to Aug. of Pran Majumder PWSSunder JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000118/2023-2024 | 634/CD | 12/07/2023 | 09/12/2023 | SHRI ANNAPURNA DISTRIBUTORS | 218.17 | 49.08 | 22.5 | 45
4 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Providing functional house hold tap connection within command area of PRAN MAJUMDER Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000141/2022-2023 | 215/MTB | 26/07/2022 | 10/08/2022 | SANJAY MANDAL | 4.8 | 4.8 | 99.95 | 1
5 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Providing functional house hold tap connection within command area of Pranmajumder Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000148/2022-2023 | 212/MTB | 26/07/2022 | 10/08/2022 | NORTHE BENGAL CONST CO | 4.69 | 4.69 | 100 | 1
6 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000426/2023-2024 | 1482/CD | 20/12/2023 | 18/02/2024 | SHRI ANNAPURNA DISTRIBUTORS | 96.67 | 0 | 0 | 66
7 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION PART C | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000485/2023-2024 | 287/CD | 09/02/2024 | 09/04/2024 | SHRI ANNAPURNA DISTRIBUTORS | 96.22 | 24.97 | 25.95 | 51
8 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PMAJUMDER & G CHOWRANGEE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000550/2023-2024 | 608/CD | 11/03/2024 | 10/05/2024 | SHRI ANNAPURNA DISTRIBUTORS | 84.76 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000607/2023-2024 | 657/CD | 11/03/2024 | 10/05/2024 | SHRI ANNAPURNA DISTRIBUTORS | 24.67 | 0 | 0 | 30
10 | COOCHBEHAR |  | Northern Mechanical Division II | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Electric Quotation Bill for NSC at PRANMAJUMDER (AUG) |  |  | BILL/02236/2023-2024 | BP-2023-24-490 | 21/12/2023 |  | WBSEDCL | 5.23 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME TW No.-I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/001134/2023-2024 | 2881/NMD-II | 17/10/2023 | 16/11/2023 | M/S. SAMRIDDHI ENTERPRISE | 11.69 | 0 | 0 | 0
Total | [13 empty] | 550.38 | 83.53 | 15.18