## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Panisala PWSS. | SM/16526 | Augmentation | EXECUTION OF DIFFERENT WORK AT PANISALA PWSS |  |  | BILL/01998/2023-2024 | BP-1392 | 30/03/2024 |  | GOUTAM KUMAR DAS | 2.89 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Panisala PWSS. | SM/16526 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Panisala PWSS. | SM/16526 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 111/CD | 26/04/2023 |  | Resource Division | 14.12 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Panisala PWSS. | SM/16526 | Augmentation | SUPPLEMENTARY QUOTATION FOR EFFECTING NSC PANISALA III (AUG) VIDE APP NO 4003094006 AGAINST INFRASTRUCTURE DEV COST. |  |  | BILL/00170/2023-2024 | BP-2023-24-129 | 19/05/2023 |  | WBSEDCL | 11.42 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Panisala PWSS. | SM/16526 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF PANISALA PWSS , TW No.- Iunder NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000756/2023-2024 | 2337/NMD-II | 01/08/2023 | 31/08/2023 | INDRAJIT MITRA | 10.66 | 0 | 0 | 50
Total | [13 empty] | 19828.38 | 0 | 0