## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to BHERBHERI PWSS under JAL JEEVAN MISSION Behar Division, PHED |  |  | ORD/000070/2024-2025 | 3998 | 06/06/2024 | 04/09/2024 | SHREE RANI SATI ENTERPRISE | 83.55 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000320/2023-2024 | 1303/CD | 24/11/2023 | 22/02/2024 | UDAY CHAKI | 4.92 | 2.37 | 48.16 | 96
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000365/2023-2024 | 1362/CD | 05/12/2023 | 03/02/2024 | M/S KAMAK ENGINEERS AND CO | 96.35 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1313/1-5/NBC-1; Dt.: 20-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000612/2022-2023 | 1932/CD | 22/03/2023 | 19/08/2023 | M/S KAMAK ENGINEERS AND CO | 619.31 | 182.21 | 29.42 | 40
6 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 184/CD | 27/04/2023 |  | Resource Division | 14.9 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 21/CD | 05/01/2024 |  | Resource Division | 19.88 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JORESIMULI TW I. |  |  | BILL/00517/2024-2025 | BP-118/24-25 | 24/05/2024 |  | WBSEDCL | 3.75 | 0 | 0 | null
9 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JORESIMULI TW II. |  |  | BILL/00641/2024-2025 | BP-160/24-25 | 21/06/2024 |  | WBSEDCL | 3.1 | 0 | 0 | null
10 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jore Simuli water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/001087/2023-2024 | 2787/NMD-II | 06/10/2023 | 05/11/2023 | A.S. ENTERPRISE | 21.65 | 0 | 0 | 0
Total | [13 empty] | 20656.71 | 184.58 | 0.89